## deliverables
| id | code | work_package | description | month_due | progress | percent | partner
0 | 343 | D-R1.1 | WP-R1 | Report on current state of knowledge regarding user needs for forecasts at different timescales in each sector. | 9 | Submitted on 12th July 2018 | 0 | UoL
1 | 344 | D-R1.2 | WP-R1 | A report on user perceptions and needs for forecast products for different timescales and sectors in each country. | 27 | Planned completion revised to December 2019 to reflect change in task schedule. | 0 | KNUST
2 | 345 | D-R1.3 | WP-R1 | Coproduced forecast communication tools that have been iteratively tested and refined with user groups, and recommendations for good practice. | 41 | Planned completion revised to February 2021 to reflect revised schedule. Elias Nikiaka's contract has been ammended due to his work being part time until August 2018. However he is still scheduled to finish in April 2020 | 0 | UoL
3 | 346 | D-R1.4 | WP-R1 | Joint deliverable with WP-R2: User evaluation of forecast utility developed through direct provider/user interaction and user feedback in 1.2.2a-d, and guide to impact based forecasting | 45 | Not yet begun. | 0 | UoL
4 | 347 | D-R2.1 | WP-R2 | Reports describing the implementation of eye-witness reports, radar and satellite observations over Africa for verification of severe weather forecasts (both synoptic and NWP). | 26 | 2% complete. Data gathering ongoing. | 2 | KNUST
5 | 349 | D-R2.3 | WP-R2 | Reports describing implementation of new metrics for CP ensemble evaluation against satellite data. | 11 | 2% complete. Case studies identified. WP-R7 explained case study design and selection procedure. | 2 | FUTA
6 | 350 | D-R2.4 | WP-R2 | Reports on design and implementation of verification metrics for S2S and probabilistic forecasts and developments to seamless evaluation methodology. | 11 | 5% complete. Case studies identified. | 5 | ICPAC
7 | 351 | D-R2.5 | WP-R2 | Documentation on best practice for forecast evaluation over Africa. | 26 | Not yet begun. | 0 | FUTA
8 | 352 | D-R2.6 | WP-R2 | Training school on best practice for forecast evaluation over Africa. | 38 | Not yet begun. | 0 | UoR
9 | 353 | D-R2.7 | WP-R2 | Baseline evaluation of weather forecast skill and updates as the project evolves, for M&E. | 11 | 2% complete. Met services have provided forecast products that they intend to verify during SWIFT. | 2 | UoR
10 | 354 | D-R2.8 | WP-R2 | Joint deliverable with WP-R2: User evaluation of forecast utility, and guide to impact based forecasting | 45 | Not yet begun. | 0 | UoL
11 | 355 | D-R3.1 | WP-R3 | Establish a new UK research capability in satellite remote sensing of clouds | 25 | 20% complete. The grade 8 position has been filled; Jennifer Fletcher will start in Nov, 2018. The other position will be filled in Jan 2019 and then the networking etc will begin. | 20 | NCAS-AP
12 | 356 | D-R3.2 | WP-R3 | Report on current status of satellite and radar products used in operational centres and universities. Baseline exercise | 13 | 70% complete middle of Sept 18. A survey is being sent out on 17 August 18 with a due date a week or so later. The report will be written shortly thereafter. It has already been established that none of the African partners are using the EUMETSAT nowcasting system for forecasts. | 70 | UCAD
13 | 357 | D-R3.3 | WP-R3 | Make satellite products available to African centres | 23 | 30% complete approximately. Difificult to determine since the task is so involved. The plan is to get the EUMETSAT products working in UoL on a local compute. Then take disks, or laptops with everything set up and working to the African partners and teach them how to use the products. A satellite dish and decoder will have to be bought by the African parnters for streaming the EUMETSAT data in real time. | 30 | NCAS-AP
14 | 358 | D-R3.4 | WP-R3 | Enhanced capacity in African centres for analysing satellite data (all relevant channels) and using satellite products -- as evidenced by good access to products, trained users, training material, use in interpretation of convective rainfall and how best to use in nowcasting. | 47 | Not yet started | 0 | ACMAD
15 | 359 | D-R3.5 | WP-R3 | Phase 1. Case/satistical studies of evolution of storms using satellite products. | 27 | 5% completed. There has been some progress on this deliverable, but good cases still need to be chosen. | 100 | NCAS-AP
16 | 360 | D-R3.6 | WP-R3 | New well-tested satellite product for improved nowcasting capability | 39 | Not yet started | 0 | UoL
17 | 361 | D-R3.7 | WP-R3 | Phase 2. In-depth study of physical processes (dynamics and microphysics) in storms using more advanced satellite data | 48 | Not yet started | 0 | NCAS-AP
18 | 363 | D-R4.1 | WP-R4 | Access to an automated satellite-based storm nowcasting tool/product in SWIFT centres | 51 | 15% NWC SAF working at UoL NCAS with test data | 15 | ANACIM
19 | 365 | D-R4.3 | WP-R4 | Documented new scientific understanding of: (i) behaviour of convective storms in West and East Africa & dependence on local environment, (ii) the observed relationships between remotely-sensed storm properties and in-situ observations of high-impact weather, with peer-reviewed publications | 51 | 0% - awaiting UoL NCAS PDRA to start | 0 | NCAS-AP
20 | 367 | D-R5.1 | WP-R5 | Benchmark current operational practice (project document) | 15 | 40% complete - key tasks to achieve this deliverable have been strated | 40 | UoL
21 | 368 | D-R5.2 | WP-R5 | Benchmark current state of knowledge on synoptic systems and HIW over West Africa (project document) | 15 | 30% complete approximately | 30 | NiMet
22 | 369 | D-R5.3 | WP-R5 | Benchmark current state of knowledge on synoptic systems and HIW over East Africa (project document) | 15 | 30% complete approximately | 30 | UoL
23 | 370 | D-R5.4 | WP-R5 | Investigate and evaluate physical processes of synoptic systems in reanalysis | 27 | Not yet started | 0 | UoL
24 | 371 | D-R5.5 | WP-R5 | Evaluate representation of synoptic system in models, i.e. in global and convection-permitting deterministic and ensemble simulations with the MetUM, as well as other operatinally used models such as WRF and COSMO to determine the predictability of deep convection in different synoptic environments in Africa | 51 | Not yet started | 0 | UoL
25 | 372 | D-R5.6 | WP-R5 | Develop new training material on the realtionship between the synoptic and the meso-scale (e.g. case studies) | 51 | Not yet started | 0 | FUTA
26 | 373 | D-R6.1 | WP-R6 | Scientific papers on sub-seasonal drivers of variability | 51 | Benchmarking of knowledge of sub-seasonal drivers continues and research has begin on the role of MJO, AEJ and TEJ on W African Monsoon Onset. | 5 | NCAS-C
27 | 362 | D-R3.8 | WP-R3 | Land-surface analysis | 27 | This work (characterising land persistence in response to rain from EO) won't start till April 2020 | 0 | CEH
28 | 375 | D-R6.3 | WP-R6 | Document(s) on assessment of forecast skill | 51 | Initial analysis of forecast skill underway | 0 | ICPAC
29 | 376 | D-R6.4 | WP-R6 | New documented operational products and tools | 51 | Not started | 0 | ACMAD
30 | 377 | D-R6.5 | WP-R6 | Documentation on operational best practice | 51 | Benchmarking survey's of current operational practice analysed and benchmarking report in preparation | 0 | ANACIM
31 | 378 | D-R6.6 | WP-R6 | Training materials for summer schools | 35 | Preparation fo training materials awaiting decsions on oveally content of summer school | 0 | NCAS-C
32 | 379 | D-R6.7 | WP-R6 | Updated chapter(s) for forecasters handbook | 45 | Not started | 0 | NCAS-C
33 | 380 | D-R6.8 | WP-R6 | S2S forecast testbed | 39 | Planning for the testbed has begun: The format of fortnightly telecons has been agreed. | 0 | ICPAC
34 | 381 | D-R7.1 | WP-R7 | Benchmark current state of knowledge and best practice in convection-permitting ensemble forecasting (project document) | 9 | Delayed due to delay in PDRA recruitment. This task will be assigned to WP-R7 convective ensembles PDRA Beth Woodhams, who starts in April 2019. It will be the first task she performs. New deadline May 2019. | 0 | UoL
35 | 382 | D-R7.2 | WP-R7 | Creation of a set of CP ensemble forecasts over tropical Africa and prototype post-processed products for research and training. For use by Africa-SWIFT academics and African partners. The forecast data will be available on the Met Office MASS archive for UK academics and will be packaged up appropriately to send to partners as needed. Post-processed products will be provided for the testbeds and other training activities. | 39 | 5% complete. At the last WP-R7 meeting the strategy for selecting case study dates was discussed. Partners from across the WPs have suggested interesting case studies. Stu Webster has run one test simulation (as of 17/08/2018). Sam Clarke, who starts 20th Aug. 2018 will analyse that simulation to check everything is working ok, then we will start running further simulations. Deadlines on track. | 5 | UKMO
36 | 383 | D-R7.3 | WP-R7 | Report on evaluation of ensemble forecast skill and optimal model configuration | 43 | Beth Woodhams will complete this task when she starts in April 2019. Deadline on track. | 0 | UoL
37 | 384 | D-R7.4 | WP-R7 | Report on storm predictability under different synoptic conditions in the context of CP ensemble forecasting | 51 | Will be jointly completed by WP-R5 and R7 PDRAs (Woodhams and Clarke, starting Apr 2019 and Aug 2018 respectively). Deadline on track. | 100 | UoL
38 | 388 | D-C2.2 | WP-C2 | Documentation on Testbed 1 including a paper. | 27 | Planned for April 2019 | 0 | UoL
39 | 389 | D-C2.3 | WP-C2 | Carry out Testbed 2 (S2S) | 33 | Planned for April 2019 | 0 | ICPAC
40 | 390 | D-C2.4 | WP-C2 | Documentation on Testbed 2. Papers. | 39 | Planned for April 2019 | 0 | ICPAC
41 | 391 | D-C2.5 | WP-C2 | Carry out Testbed 3 (nowcasting to synoptic) | 49 | TBD | 0 | UoL
42 | 392 | D-C2.6 | WP-C2 | Documentation on Testbed 3. Papers. | 49 | TBD | 0 | UoL
43 | 393 | D-M1.1 | WP-M1 | Kick-off meeting | 2 | Completed November 2017 | 100 | UoL
44 | 394 | D-M1.2 | WP-M1 | Assurance Documentation | 12 | Completed September 2018 | 100 | NCAS-AP
45 | 395 | D-M1.3 | WP-M1 | Due Diligence | 6 | Ongoing - 80% complete | 0 | NCAS-AP
46 | 396 | D-M1.4 | WP-M1 | Collaboration Agreement | 6 | Completed March 2018 with amendment to insurance request for African partners in August 2018 | 100 | NCAS-AP
47 | 398 | D-M1.6 | WP-M1 | Financial Management Plan | 6 | Completed March 2018 with amendments made September 2018 | 100 | NCAS-AP
48 | 399 | D-M1.7 | WP-M1 | Recruitment | 6 | Completed September 2018 | 100 | UoL
49 | 400 | D-M1.8 | WP-M1 | Budgeting & Finance protocol | 12 | Completed March 2018 with amendments made September 2018 | 100 | NCAS-AP
50 | 402 | D-M1.10 | WP-M1 | Leadership of cross-cutting activities such as fellowships, secondments, summer schools, etc. | 51 | 70% complete - to be finalised September 2018 | 70 | NCAS-AP
51 | 403 | D-M1.11 | WP-M1 | SWIFT 4-Year Plan (calendar of events) | 12 | 70% complete - to be finalised September 2018 | 70 | NCAS-AP
52 | 404 | D-M1.12 | WP-M1 | Scientific reporting | 51 | 70% complete - to be finalised September 2018. First tranche of reporting collected September 2018 | 70 | UoL
53 | 405 | D-M1.13 | WP-M1 | Monitoring indicators (MEL) and MEL protocol | 12 | 70% complete - to be finalised September 2018 | 70 | NCAS-AP
54 | 406 | D-M1.14 | WP-M1 | LogFrame and ToC | 12 | Completed September 2018 | 100 | NCAS-AP
55 | 407 | D-M1.15 | WP-M1 | Communications Strategy | 9 | Completed June 2018 | 100 | NCAS-AP
56 | 408 | D-M1.16 | WP-M1 | Data protocol plan | 12 | In development | 0 | NCAS-AP
57 | 410 | D-M1.18 | WP-M1 | Stage Gate Review | 12 | Completed September 2018 | 100 | NCAS-AP
58 | 411 | D-M1.19 | WP-M1 | Annual reporting to RCUK/GCRF | 18 | Ongoing - first tranche completed September 2018 | 100 | NCAS-AP
59 | 412 | D-M1.20 | WP-M1 | Whole project meeting 2019 | 16 | TBC July 2019 | 0 | NCAS-AP
60 | 413 | D-M1.21 | WP-M1 | Whole project meeting 2020 | 16 | TBC 2020 | 0 | NCAS-AP
61 | 414 | D-M1.22 | WP-M1 | Whole project meeting 2021 | 16 | TBC 2021 | 0 | NCAS-AP
62 | 417 | D-M1.25 | WP-M1 | Science Programme Director to travel to African Partner Institutions | 41 | SPD appointed October 2018 | 0 | ACMAD
63 | 386 | D-C1.10 | WP-C1 | Fellowships: advertise, assess and appoint. | 11 | First 3 fellows appointed on schedule. Second round to be advertised (probably need to create a new deadline for this, for the deliverable. Need to discuss schedule for next round. | 60 | NCAS-AP
64 | 387 | D-C2.1 | WP-C2 | Carry out Testbed 1 | 21 | Planned for April 2019 Testbed 1a completed successfully. Planning group is active. | 20 | UoL
65 | 401 | D-M1.9 | WP-M1 | Meetings: Exec, Advisory, WPs | 51 | Ongoing throughout the project, but protocol for meetings developed | 80 | NCAS-AP
66 | 397 | D-M1.5 | WP-M1 | Risk Register | 6 | Draft finaliased March 2018, but ongoing throughout the project | 80 | NCAS-AP
67 | 409 | D-M1.17 | WP-M1 | Communications: website, promotional materials, advertising, coordination of articles published, logo, etc. | 12 | Website and logo finalised in April 2018. | 80 | NCAS-AP
68 | 415 | D-M1.23 | WP-M1 | Documentation workshop | 30 | First meeting held in Nairobi, Jan 2019. Second meeting to be held in project meeting, Kumasi, 2019. | 50 | NCAS-AP
69 | 418 | D-M1.26 | WP-M1 | Aligning the WPs (cross-cutting activities) | 14 | SPD appointed October 2018 | 0 | ACMAD
70 | 419 | D-M1.27 | WP-M1 | Development of best practice for university funded GCRF programmes | 14 | 60% complete. Lorraine Youds has written a paper, together with a colleague, on joining-up the project development stage and project initiation stage of programmes and a review of current procedures at the University of UoL to ensure that they are fitfor-purpose for large, international, multi-partner programmes. | 60 | NCAS-AP
71 | 420 | D-M2.1 | WP-M2 | Partnerships: a coordinated set of partnerships which contribute to the SWIFT outcomes. | 14 | Still in development - partnerships have been developed with several global weather programmes and businesses, e.g. BP, HIGHWAY, the YESS network, Rainwatch | 0 | ACMAD
72 | 421 | D-M2.2 | WP-M2 | Documentation of user-needs methodologies. This could be a new Forecasters' Handbook chapter - to be discussed. | 21 | TBD - PSD appointed October 2018 | 0 | ACMAD
73 | 422 | D-M2.3 | WP-M2 | New Handbook chapter on Forecast Evaluation | 39 | TBD - PSD appointed October 2018 | 0 | ACMAD
74 | 423 | D-M2.4 | WP-M2 | Updated Handbook material on Nowcasting for Africa. | 39 | TBD - PSD appointed October 2018 | 0 | ACMAD
75 | 424 | D-M2.5 | WP-M2 | Updated Handbook material on ensemble prediction for Africa. | 39 | TBD - PSD appointed October 2018 | 0 | ACMAD
76 | 425 | D-M2.6 | WP-M2 | Updated Handbook material on S2S forecasting for West Africa. | 39 | TBD - PSD appointed October 2018 | 0 | ACMAD
77 | 426 | D-M2.7 | WP-M2 | Produce a Forecasters' Handbook for East Africa. | 51 | TBD - PSD appointed October 2018 | 0 | ACMAD
78 | 366 | D-R4.4 | WP-R4 | Recommendations on best storm nowcasting practise for the SWIFT region, with appropriate training products and activities | 51 | 15%% survey of existing practices underway, some work started during the Pre test bed 1a | 15 | KMD
79 | 374 | D-R6.2 | WP-R6 | Scientific papers on S2S model evaluation | 51 | 1. Analysis of subseasonal forecast skill for Africa in NCEP, ECWMF and Met Office models is underway, and a paper is in preparation 2. Analysis of forecast skill for Monsoon Onset for CMA, Met Office and ECMWF over Nigeria has been carried out and a paper is in preparation. | 5 | NCAS-C
80 | 348 | D-R2.2 | WP-R2 | Joint deliverable with WP-R4: Reports on nowcasting evaluation against satellite data using new metrics. | 11 | The work has begun already in Ghana where analysis on weather related elements have been investigated and documented through daily and weekly "Chart Discussions" at the GMet Central Analysis and Forecast Office (CAFO). | 60 | GMet
81 | 364 | D-R4.2 | WP-R4 | Documented evaluation of selected automated Nowcasting tool | 51 | GMet in Ghana do not have automated nowcasting tools but the nowcasting is done manually, where models are analysed and synoptic features interpreted to come out with weather forecast. | 60 | GMet
82 | 385 | D-C1.8 | WP-C1 | Summer school 1: many sub-tasks | 10 | Postpone to July 2019 (might have been typo, originally?). Planning will start in earnest in September 2018 at KNUST. We will partner the event with YESS. Planning group is active. Advert has now been sent around. | 30 | UoL
83 | 416 | D-M1.24 | WP-M1 | Lead Scientist and Programme Manager travel to partner institutions | 30 | Started November 2018 - ongoing. Doug Parker and Lorriane Youds have visted Dakar, Senegal and Nairobi, Kenya. Visit to Accra and Kumasi, Ghana completed in September 2018. Due to a reduction in travel commitments, Doug will not go to Nigeria in Spring 2019, but Lorraine plans to go, to coincide with the Users meeting. | 75 | NCAS-AP

## partners
| id | name | country | role
0 | 86 | NCAS-AP | UK | Academic
1 | 87 | NCAS-C | UK | Academic
2 | 88 | UoL | UK | Academic
3 | 89 | UoR | UK | Academic
4 | 90 | CEH | UK | Academic
5 | 91 | UKMO | UK | Operational
6 | 92 | ACMAD | International | Academic
7 | 93 | ICPAC | International | Academic
8 | 94 | ANACIM | Senegal | Operational
9 | 95 | UCAD | Senegal | Academic
10 | 96 | GMet | Ghana | Operational
11 | 97 | KNUST | Ghana | Academic
12 | 98 | NiMet | Nigeria | Operational
13 | 99 | FUTA | Nigeria | Academic
14 | 100 | KMD | Kenya | Operational
15 | 101 | UoN | Kenya | Academic
16 | 102 | WMO | Switzerland | Operational

## tasks
| id | code | description | month_due | progress | percent | work_package | partner
0 | 428 | T-R1.1.1 | Development of reporting template for baselining the current provision of forecasts | 4 | Initial version completed Jan 31st 2018. Ammended and finalised on 9th Feb 2018 (based on Met Office feedback) | 100 | WP-R1 | UoL
1 | 429 | T-R1.1.2 | Documentations of governance and institutional arrangements for NMSs | 14 | Work ongoing. Revised planned completion date November 2018 | 0 | WP-R1 | KNUST
2 | 430 | T-R1.1.3a | Completion of 1.1.1 reporting templates for Ghana | 7 | Final version received 13th April 2018 | 0 | WP-R1 | KNUST
3 | 432 | T-R1.1.3c | Completion of 1.1.1 reporting templates for Nigeria | 7 | Final version received 5th May 2018 | 0 | WP-R1 | NiMet
4 | 433 | T-R1.1.3d | Completion of 1.1.1 reporting templates for Senegal | 7 | Final version received 27th April 2018 | 0 | WP-R1 | ANACIM
5 | 434 | T-R1.1.4 | Draft paper reviewing exisiting literature (peer review and grey literature) on user needs for weather and climate information in West Africa and East Africa | 9 | Draft completed June 2018, final deliverable report submitted on 12 July 2018 | 100 | WP-R1 | UoL
6 | 435 | T-R1.2.1 | Completion of standard protocols for user surveys and interviews | 14 | Delayed due to desire to use outputs of the user-provider workshops in developing protocols. However, due to unavoidable delays holding the workshops, this task will now proceed regardless. New target month is October 2018. Philip Antwi-Agyei to take leadership until ACMAD post appointed. | 0 | WP-R1 | UoL
7 | 436 | T-R1.2.2a | ACMAD faciliated workshops bringing together NMS and user representatives in each partner country (Ghana) | 14 | Delayed due to challenges in filling ACMAD WP-R1 facing post. An outline to guide the workshops is being developed by WP leads in collaboration with the UKMO and NMSs in each partner countries. A final completion date of Feb 2019 has been indicated due to uncertainties around availability and the ACMAD position. However, it is planned that the workshop will take place before this month (current target October 2018). Andrea Taylor to take leadership until ACMAD post appointed. | 0 | WP-R1 | ACMAD
8 | 437 | T-R1.2.2b | ACMAD faciliated workshops bringing together NMS and user representatives in each partner country (Kenya) | 14 | It has been proposed that the workshop in Nairobi be delayed until Jan 2019 in order to tie in with testbed planning. | 0 | WP-R1 | ACMAD
9 | 438 | T-R1.2.2c | ACMAD faciliated workshops bringing together NMS and user representatives in each partner country (Nigeria) | 17 | Delayed due to challenges in filling ACMAD WP-R1 facing post. New proposed timing of November 2018 (although discussions still taking place with NMS). An outline to guide the workshops is being developed by WP leads in collaboration with the UKMO and NMSs in each partner countries. A final completion date of Feb 2019 has been indicated due to uncertainties around availability and the ACMAD position. However, it is planned that the workshop will take place before this month (current target November 2018) Andrea Taylor to take leadership until ACMAD post appointed. | 0 | WP-R1 | ACMAD
10 | 439 | T-R1.2.2d | ACMAD faciliated workshops bringing together NMS and user representatives in each partner country (Senegal) | 17 | Delayed due to challenges in filling ACMAD WP-R1 facing post. New proposed timing of October 2018 although discussions still taking place with NMS). An outline to guide the workshops is being developed by WP leads in collaboration with the UKMO and NMSs in each partner countries. A final completion date of Feb 2019 has been indicated due to uncertainties around availability and the ACMAD position. However, it is planned that the workshop will take place before this month (current target October 2018). Andrea Taylor to take leadership until ACMAD post appointed. | 0 | WP-R1 | ACMAD
11 | 440 | T-R1.2.3a | Pilotting user interviews and surveys in partner countries and identifying country strategy for conducting survey and interview strategy: Phase 1 (Ghana) | 15 | Activity initially pushed back until after user workshops. As uncertainty exists over precise workshop timing. New completion date is December 2018. | 0 | WP-R1 | KNUST
12 | 442 | T-R1.2.4a | Pilotting user interviews and surveys in partner countries and identifying country strategy for conducting survey and interview: Phase 2 (Kenya) | 17 | Activity initially pushed back until after user workshops. As uncertainty exists over precise workshop timing. New completion date is February 2019. | 0 | WP-R1 | UoN
13 | 443 | T-R1.2.4b | Pilotting user interviews and surveys in partner countries and identifying country strategy for conducting survey and interview: Phase 2 (Nigeria) | 17 | Activity initially pushed back until after user workshops. As uncertainty exists over precise workshop timing. New completion date is February 2019. | 0 | WP-R1 | NiMet
14 | 444 | T-R1.2.5a | Completion of user interviews and surveys: Phase 1 (Ghana) | 19 | Revised to April 2019 following on from changes to pilotting schedule. | 0 | WP-R1 | KNUST
15 | 445 | T-R1.2.5b | Completion of user interviews and surveys: Phase 1 (Senegal) | 19 | Revised to April 2019 following on from changes to pilotting schedule. | 0 | WP-R1 | ANACIM
16 | 446 | T-R1.2.6a | Completion of user interviews and surveys interviews: Phase 2 (Kenya) | 22 | Revised to July 2019 following on from changes to pilotting schedule. | 0 | WP-R1 | UoN
17 | 447 | T-R1.2.6b | Completion of user interviews and surveys interviews: Phase 2 (Nigeria) | 22 | Revised to July 2019 following on from changes to pilotting schedule. | 0 | WP-R1 | NiMet
18 | 448 | T-R1.2.7 | Draft paper reporting on the findings of 1.2.5a, 1.2.5b, 1.2.6a and 1.2.6b. | 26 | Revised to Nov 2019 following on from changes to inteview schedule. | 0 | WP-R1 | UoL
19 | 449 | T-R1.3.1 | Table collating evidenced based recommendations for good practice in forecast communication acquired through Tasks 1.1 and 1.2, and through continued review of the peer review and grey literature. | 31 | Revised to correspond with Elias Nkiaka's revised end of contract. | 0 | WP-R1 | UoL
20 | 450 | T-R1.3.2 | Case study examining measureable impact? (e.g. meningitis warnings, fishing fines, crop insurance etc?) | 41 | Revised to Feb 2021 to correspond with other changes in project schedule. Andrea Taylor currently takes responsibility for this. However, as this is further defined "ownership" may change. | 0 | WP-R1 | UoL
21 | 451 | T-R2.1.1 | Archive strategy for radar data | 19 | 10% complete. Lahat is making progress with data storage and server purchase. GMet have provided a report on their radar availability for Accra. The old radar in Senegal is no longer operational. The new radar for the new Dakar airport will be operated by ASECNA. | 10 | WP-R2 | ANACIM
22 | 498 | T-R3.7.2 | Ghana | 27 | Not yet started | 0 | WP-R3 | KNUST
23 | 452 | T-R2.1.2 | Identify storm characteristics in dense rain gauge network and satellite data | 20 | 10% complete. Rain gauge data has been gather by Leonard and Jacob at KNUST and by David Koros at KMD. | 10 | WP-R2 | KNUST
24 | 456 | T-R2.2.1 | N/A (Requires alignment with WP-R4) | 32 | Not yet begun. | 0 | WP-R2 | NiMet
25 | 457 | T-R2.3.1 | Select case studies suitable for ensembles evaluation (WP-R7) | 33 | 10% complete. Several case studies identified for Nigeria. Case study design and selection procedure agreed with WP-R7. | 10 | WP-R2 | ACMAD
26 | 459 | T-R2.3.3 | Analysis of cases against uniform set of verification metrics | 42 | Not yet begun. | 0 | WP-R2 | ACMAD
27 | 460 | T-R2.4.1 | Select case studies based on S2S archive | 9 | 100% complete. Identified three case studies over East Africa, namely November 2015 and two in MAM 2018. For MAM 2018, most models indicated normal to below normal rainfall, but heavy floods were experienced (above normal). | 100 | WP-R2 | ICPAC
28 | 462 | T-R2.4.3 | Design S2S verification metrics | 31 | Not yet begun. | 0 | WP-R2 | ICPAC
29 | 463 | T-R2.4.4 | Analysis of case studies | 45 | 0% complete. Task commenced Aug-18. | 0 | WP-R2 | ICPAC
30 | 464 | T-R2.5.1 | Document radar use across Africa for verification | 20 | Not yet begun. | 0 | WP-R2 | ANACIM
31 | 467 | T-R2.5.4 | Document S2S verification practice | 48 | Not yet begun. | 0 | WP-R2 | ICPAC
32 | 468 | T-R2.6.1 | Link up planning with WP-C1 training and test-bed event | 16 | Not yet begun. | 0 | WP-R2 | UoR
33 | 471 | T-R2.6.4 | Online resources post-event | 16 | Not yet begun. | 0 | WP-R2 | UoR
34 | 472 | T-R2.7.1 | Identify forecasts used for baseline evaluation and relevant metrics and set reporting intervals | 51 | 5% complete. Met services have provided comprehensive responses regarding what forecasts will be used for verification. Action on WP and Strand leaders to provide guidance. | 5 | WP-R2 | FUTA
35 | 473 | T-R2.7.2 | Document at regular intervals forecast skill and metrics used | 49 | 5% complete. Met services have provided comprehensive responses regarding what forecasts will be used for verification. Action on WP and Strand leaders to provide guidance. | 5 | WP-R2 | FUTA
36 | 474 | T-R2.7.3 | Evaluate uptake of verification practices and metrics at operational centers | 48 | Not yet begun. | 0 | WP-R2 | FUTA
37 | 475 | T-R3.1.1 | Hire 2 positions within NCAS. | 16 | 50% complete. The grade 8 position has been filled; Jennifer Fletcher will start in Nov, 2018. NCAS Board has requested that the second position (Grade 6) be filled by an NCAS core person. This will require the person to work at least 50% (for 4 years) on the project, but ideally 100% for 2 years. | 50 | WP-R3 | NCAS-AP
38 | 476 | T-R3.1.2 | Establish current work in field and hold research forum | 26 | Not yet begun. | 0 | WP-R3 | NCAS-AP
39 | 477 | T-R3.2.1 | Report on the current satellite operational products used in African Centres. | 13 | 70% complete by middle of Sept 18. A survey is being sent out on 17 August 18 with a due date a week or so later. The report will be written shortly thereafter. It has already been established that none of the African partners are using the EUMETSAT nowcasting system for forecasts. | 70 | WP-R3 | ANACIM
40 | 478 | T-R3.2.2 | Report on current radar facilities and capabilities in African Centres. | 13 | Similar to above, but for radar. | 0 | WP-R3 | ANACIM
41 | 479 | T-R3.3.1 | Sort out how to access and use appropriate EUMETSAT data. | 13 | 40% complete. It�s now possible to access the data (not in real time) . | 40 | WP-R3 | NCAS-AP
42 | 480 | T-R3.3.2 | Determine products and domain required by each centre | 20 | Not yet started | 0 | WP-R3 | NCAS-AP
43 | 481 | T-R3.3.3 | Set up and deliver system with software, satellite data and images, and documentation tailored for individual centre needs | 23 | 5% complete. A start has been made on setting up the system. | 5 | WP-R3 | NCAS-AP
44 | 482 | T-R3.4.1 | Write new training materials (and/or instructions how to use exisiting material) for using satellite products. | 23 | 5% complete. Notes have been made as progress is made. | 5 | WP-R3 | NCAS-AP
45 | 483 | T-R3.4.2 | Produce web pages. | 23 | Not yet started | 0 | WP-R3 | NCAS-AP
46 | 484 | T-R3.4.3 | Train the trainers in using satellite products | 21 | Not yet started | 0 | WP-R3 | NCAS-AP
47 | 485 | T-R3.5.1 | Storms in: Senegal | 27 | Not yet started | 0 | WP-R3 | ANACIM
48 | 486 | T-R3.5.2 | Ghana | 27 | 5% completed. There has been some progress on this deliverable, but good cases still need to be chosen. | 100 | WP-R3 | KNUST
49 | 487 | T-R3.5.3 | Nigeria | 17 | Not yet started | 0 | WP-R3 | FUTA
50 | 489 | T-R3.5.5 | Africa? | 27 | Not yet started | 0 | WP-R3 | ACMAD
51 | 490 | T-R3.5.6 | Africa? | 27 | Not yet started | 0 | WP-R3 | NCAS-AP
52 | 492 | T-R3.6.1 | Define the problem to be solved | 20 | Not yet started | 0 | WP-R3 | UoL
53 | 493 | T-R3.6.2 | Design of new product & implementation | 22 | Not yet started | 0 | WP-R3 | UoL
54 | 494 | T-R3.6.3a | Implementation of new product | 26 | Not yet started | 0 | WP-R3 | UoL
55 | 495 | T-R3.6.3b | Test of new product using one or more of case studies in T-R3.5.x. | 32 | Not yet started | 0 | WP-R3 | NCAS-AP
56 | 496 | T-R3.6.4 | Make new product available to African centres. Write documents. Training of key people and set of on-line documents. | 39 | Not yet started | 0 | WP-R3 | ACMAD
57 | 497 | T-R3.7.1 | Storms in: Senegal | 41 | Not yet started | 0 | WP-R3 | UCAD
58 | 454 | T-R2.1.4 | Develop storm statistics tools for use with radar data | 20 | 0% complete. PDRA (Carlo Cafaro) started in January 2019. | 0 | WP-R2 | UoR
59 | 491 | T-R3.5.7 | Evaluate co-variation of observed storm statistics | 15 | 10% complete. PDRA (Peter Hill) has applied offline storm tracking tool on SEVIRI data. | 10 | WP-R3 | UoR
60 | 458 | T-R2.3.2 | Characterise uncertainty in verification statistics | 36 | 0% complete. PDRA (Carlo Cafaro) started in January 2019. | 0 | WP-R2 | UoR
61 | 465 | T-R2.5.2 | Document satellite use for verification | 26 | 0% complete. PDRA (Peter Hill) started in December 2018. Task relies on documenting of forward simulators. | 0 | WP-R2 | UoR
62 | 470 | T-R2.6.3 | Design lesson plan and identify teaching staff | 16 | Not yet begun. NB. Similar task is underway for preparation of Summer School. | 0 | WP-R2 | UoR
63 | 488 | T-R3.5.4 | Kenya | 27 | some case studies have been documented at KMD | 30 | WP-R3 | KMD
64 | 461 | T-R2.4.2 | Land-surface process studies | 12 | This work will not begin until April 2020 | 0 | WP-R2 | CEH
65 | 499 | T-R3.7.3 | Nigeria | 48 | Not yet started | 0 | WP-R3 | FUTA
66 | 500 | T-R3.7.4 | Kenya | 26 | Not yet started | 0 | WP-R3 | UoN
67 | 501 | T-R3.7.5 | Africa? | 48 | Not yet started | 0 | WP-R3 | ACMAD
68 | 502 | T-R3.7.6 | Africa? | 48 | Not yet started | 0 | WP-R3 | NCAS-AP
69 | 506 | T-R4.1.1 | Documented assessment of nowcasting tools & satellite products available | 13 | 70% complete by middle of Sept 18. A survey is being sent out on 17 August 18 with a due date a week or so later. The report will be written shortly thereafter. It has already been established that none of the African partners are using the EUMETSAT nowcasting system for forecasts. | 70 | WP-R4 | ANACIM
70 | 507 | T-R4.1.2 | Documented strategy for access to & development of nowcasting tools | 13 | 50%. NWC SAF identifed as akey tool and working at NCAS with test data. Plan to share working version with all SWIFT organisations. Need to document plan. | 50 | WP-R4 | ANACIM
71 | 541 | T-R7.2.4 | Development of prototype forecast products for operational forecastering | 27 | This task will be assigned to WP-R7 convective ensembles PDRA Beth Woodhams. Deadline on track | 0 | WP-R7 | UoL
72 | 508 | T-R4.2.1 | Agreed selection of case-studies (with in-situ data) of high-impact weather affecting African-SWIFT countries for evaluation | 31 | 20%. Some email discussion of some cases, and some investigation of individual cases, but yet to collate a complete list | 20 | WP-R4 | UCAD
73 | 509 | T-R4.2.2 | Agreed metrics of user-relevant high-impact weather for nowcasts | 31 | 10% Not advanced since Dakar meeting list | 10 | WP-R4 | UCAD
74 | 510 | T-R4.2.3 | Evaluation of an automated nowcasting tool for the case studies, using remotely sensed & in-situ storm properties | 51 | 5% NWC SAF working with test data at UoL, some case study analysis under way (not with NWC-SAF) | 5 | WP-R4 | UCAD
75 | 511 | T-R4.2.4 | Statistical evaluation of an automated nowcasting tool remotely sensed storm properties, for a selected hindcast period (archiving appropriate data) | 51 | 5% NWC SAF working with test data at UoL | 5 | WP-R4 | UCAD
76 | 512 | T-R4.3.1 | Archive of satellite data+retrievals & tracked storms available, with remotely sensed properties, & corresponding operational analyses or reanalyses, for target period, for analysis of storm behaviour | 27 | 0% will start once UoL NCAS PDRAs start | 0 | WP-R4 | NCAS-AP
77 | 513 | T-R4.3.2 | Archive of in-situ data of surface weather for statistical evaluation of nowcasts of surface weather, for target hindcast period | 27 | 0% will start once UoL NCAS PDRAs start | 0 | WP-R4 | NCAS-AP
78 | 514 | T-R4.4.1 | Documented base-line of current status of nowcasting within SWIFT centres | 11 | 70% centres surveyed, not all responses complete | 70 | WP-R4 | KMD
79 | 515 | T-R5.1.1 | Benchmarking reports on synoptic systems in both observations/reanalysis and models | 15 | The work on the benchmarking reports for East and West Africa is in progress. | 0 | WP-R5 | ANACIM
80 | 516 | T-R5.1.2 | Identifying case studies for East and West Africa, which can be used across the whole project | 15 | A questionaire to identify suitable case studies is drafted. | 0 | WP-R5 | UoL
81 | 517 | T-R5.3.1 | Developing objective tracking methods for synoptic scale disturbances in reanalysis and model data | 27 | An objective tracking method has beeen developed and was presented at the last teleconference for WP-R5. | 0 | WP-R5 | ACMAD
82 | 518 | T-R5.3.2 | Providing a data set of objectively identified synoptic systems in reanalysis data | 27 | Work on objectively identyfying HIW weather events is in progress. | 0 | WP-R5 | ACMAD
83 | 520 | T-R5.3.3 | Comparing model performance on selected case studies | 27 | Work is in progress. | 0 | WP-R5 | ACMAD
84 | 521 | T-R5.4.1 | Controls on HIW through physical process studies in models and observations | 51 | Work has now started in all institutions. | 0 | WP-R5 | UCAD
85 | 522 | T-R5.3.4 | Statistical evaluation physical processes of model, analysis and reanalysis data | 51 | The work is in process. | 0 | WP-R5 | UoN
86 | 523 | T-R5.3.5 | Discuss new results on the scale interactions between the meso, synoptic and large-scale over West and East Africa at a meeting and, if possible, update or reformulate existing conceptual models | 51 | We will use the upcoming teleconference to discuss the scietific results from WP-R5. | 0 | WP-R5 | UoN
87 | 524 | T-R5.3.6 | Testing which aspects of existing synoptic models over West Africa are represented in state-of-the-art NWP models at different horizontal resolutions | 51 | Not yet begun. | 0 | WP-R5 | ACMAD
88 | 525 | T-R6.5.1 | Benchmark current operational practice | 51 | Survey complete and initial analysis presented to WP telecon. Document in prepatation | 0 | WP-R6 | ICPAC
89 | 526 | T-R6.1.1 | Benchmark current state of knowledge | 51 | Initial review of current understanidng underway: | 0 | WP-R6 | UoN
90 | 527 | T-R6.3.1 | Assess forecast skill of operational systems | 51 | Initial analysis of S2S skill underway | 0 | WP-R6 | NiMet
91 | 529 | T-R6.2.1 | Analysis of operational model representation of sub-seasonal drivers of variability | 51 | Work not started | 0 | WP-R6 | ACMAD
92 | 531 | T-R6.2.3 | Developing methods to identify tropical waves in real-time forecasts and reanalysis data | 27 | Preliminary work on idenitification of tropical waves in observations and forecasts underway | 0 | WP-R6 | UCAD
93 | 532 | T-R6.1.3 | Identifying case studies for East and West Africa, which can be used across the whole project (e.g. CP ensembles, devlopment of training materials) | 15 | Contributed to initial case study identification for WP-R7 | 0 | WP-R6 | NiMet
94 | 534 | T-R6.7.1 | Training: Testbeds | 39 | Initial Planning has begun including format and timing of testbed. | 0 | WP-R6 | ICPAC
95 | 505 | T-R3.8.2 | Analysis of persistence of observed land surface variables (LST, LAI) from historical record to inform S2S work. Paper and inclusion in S2S workshop material? | 27 | This work will not begin until April 2020 | 0 | WP-R3 | CEH
96 | 533 | T-R6.1.4 | Analysis of convective permitting ensembles to identify mechanisms of sub-seasonal influence on convective and synoptic scale variability | 51 | Work not started yet | 0 | WP-R6 | NCAS-C
97 | 530 | T-R6.2.2 | Analysis of regime dependent skill of operational forecast systems | 51 | Some work on regime dependent skill for ENSO and MJO has begun | 2 | WP-R6 | NCAS-C
98 | 528 | T-R6.1.2 | Analysis of observations and reanalysis to identify major drivers of sub-seasonal variability (e.g., MJO, ENSO, QBO, Saharan Heat low, tropical waves, African Monsoon System, land surface)" | 51 | Benchmarking of knowledge of sub-seasonal drivers continues and research has begin on the role of MJO, AEJ and TEJ on W African Monsoon Onset. | 5 | WP-R6 | NCAS-C
99 | 535 | T-R6.6.2 | Training: Summer Schools | 36 | Not yet started | 0 | WP-R6 | UoN
100 | 536 | T-R7.1.1 | Benchmarking reports on the state-of-the-art in the evaluation and operational use of CP ensembles. | 9 | Delayed due to delay in PDRA recruitment. This task will be assigned to WP-R7 convective ensembles PDRA Beth Woodhams, who starts in April 2019. It will be the first task she performs. New completion date=May 2019. | 0 | WP-R7 | UoL
101 | 537 | T-R7.2.1 | Identifying suitable dates for CP ensemble simulations | 9 | 80% complete. At the last WP-R7 meeting the strategy for selecting case study dates was discussed. Partners from across the WPs have suggested interesting case studies. Stu Webster has run one test simulation (as of 17/08/2018). The rest of this work will be on-going as we analyse incresing numbers of the simulations. | 80 | WP-R7 | UoL
102 | 538 | T-R7.2.2 | Running CP ensemble tests and conducting initial evaluation | 15 | 30% complete. Test simulation now exisits. Sam Clarke, who starts 20th Aug 2018 will analyse the test simulation to check everything is working ok, then we will start running further simulations. | 30 | WP-R7 | UKMO
103 | 539 | T-R7.2.3 | Running the full set of CP ensemble simulations | 39 | 2% complete. One test simulation is complete. Once this is analysed and the case study dates finalised it will be much quicker to run the rest. Deadline on track. | 2 | WP-R7 | UKMO
104 | 540 | T-R7.3.1 | CP ensemble model evaluation vs. global/deterministic forecasts and observations | 39 | Beth Woodhams will perform this task. Deadline on track. | 0 | WP-R7 | UoL
105 | 542 | T-R7.4.1 | Analysis of storm predictability under different symoptic conditions within an ensemble forecasting framework | 51 | Will be jointly completed by WP-R5 and R7 PDRAs (Woodhams and Clarke, starting Apr 2019 and Aug 2018 respectively). Deadline on track | 100 | WP-R7 | UoL
106 | 544 | T-C1.1.1 | Create skills matrices. | 9 | Not started (ACMAD post not yet filled). | 0 | WP-C1 | ACMAD
107 | 545 | T-C1.1.2 | Collect skills data N times. | 48 | First tranche of African researcher skills data collection completed by August 2018 | 100 | WP-C1 | ACMAD
108 | 546 | T-C1.2.1 | Collect documents describing subject benchmarks for different roles. Identify gaps where benchmarks do not already exist. | 6 | Not started (ACMAD post not yet filled). | 0 | WP-C1 | ACMAD
109 | 548 | T-C1.2.3 | Review priority syllabus development areas. | 24 | Not started (ACMAD post not yet filled). | 0 | WP-C1 | UoL
110 | 550 | T-C1.3.2 | Review outcomes of secondments. | 36 | Secondments not yet started | 0 | WP-C1 | ACMAD
111 | 551 | T-C1.4.1 | Create teaching materials (e.g. powerpoints) from the Forecasters' Handbook chapters. | 12 | Not started (ACMAD post not yet filled). Postpone to December 2018. | 0 | WP-C1 | ACMAD
112 | 552 | T-C1.4.2 | Create teaching materials from new SWIFT research in WP-R1-7. | 48 | Not yet started | 0 | WP-C1 | ACMAD
113 | 553 | T-C1.4.3 | Collaborate with Met Office to enhance International Meteorologist training | 36 | Not yet started | 0 | WP-C1 | UoL
114 | 554 | T-C1.8.1 | Review outcomes of fellowships. | 36 | Not yet started | 0 | WP-C1 | ACMAD
115 | 556 | T-C2.1.2 | Baseline assessment of forecaster-researcher links in relation to Africa. | 15 | Not yet started | 0 | WP-C2 | ACMAD
116 | 559 | T-C2.3.1 | Define programme, aims, logistics, schedules etc for Testbed 2. Many sub-tasks. | 13 | Started and meeting regarding event aims and objectives held in September 2018 | 0 | WP-C2 | ICPAC
117 | 560 | T-C2.4.1 | Washup event Testbed 2. | 33 | Not yet begun. | 0 | WP-C2 | ICPAC
118 | 561 | T-C2.5.1 | Define programme, aims, logistics, schedules etc for Testbed 3. Many sub-tasks. | 37 | Started and meeting regarding event aims and objectives held in September 2018 | 0 | WP-C2 | UoL
119 | 562 | T-C2.6.1 | Washup event Testbed 3. | 45 | Not yet begun. | 0 | WP-C2 | UoL
120 | 453 | T-R2.1.3 | Review of microwave forward simulators | 20 | 20% complete. PDRA (Peter Hill) has done a preliminary review of the literature as well as a review of simulators used in the Met Office model. A deadline for a draft report has been set for April 2019, prior to Testbed 1b. | 20 | WP-R2 | UoR
121 | 455 | T-R2.1.5 | Develop storm statistics tools for use with satellite data | 20 | 10% complete. PDRA (Peter Hill) has applied offline storm tracking tool on SEVIRI data. | 10 | WP-R2 | UoR
122 | 469 | T-R2.6.2 | Prepare lecture and exercise materials (Python scripts, sample data) | 16 | Not yet begun. NB. Similar task is underway for preparation of Summer School. | 0 | WP-R2 | UoR
123 | 503 | T-R3.7.7 | Evaluate co-variation of observed storm statistics | 27 | Not yet begun. | 0 | WP-R3 | UoR
124 | 431 | T-R1.1.3b | Completion of 1.1.1 reporting templates for Kenya | 7 | completed | 100 | WP-R1 | KMD
125 | 466 | T-R2.5.3 | Document other verification practice (rain gauges, damage reports, AWS) | 44 | Verification data,verification results and exchange of best verification practices through test bed 1a on 24th to 29th Jan 2019 are ready. | 35 | WP-R2 | KMD
126 | 519 | T-R5.1.3 | Identifying the key synoptic features over East Africa | 15 | First draft of the benchmarking report for East Aftica "Synoptic Systems and High Impact Weather over Eastern Africa" by Jemimah Gacheru is finished.First draft of the paper sent to the WP lead in August 2018 . | 40 | WP-R5 | KMD
127 | 547 | T-C1.2.2 | Agree and document priority syllabus development areas, to include "hard" and "soft" skills. | 12 | Not started (ACMAD post not yet filled). Responsibility to pass to ACMAD or ANO once ACMAD post is filled. Need to postpone due date to month 18. | 0 | WP-C1 | UoL
128 | 549 | T-C1.3.1 | Create secondment call, including criteria, process, assessment committee. | 12 | Postpone to December 2018 Postpone to June 2019. | 0 | WP-C1 | NCAS-AP
129 | 557 | T-C2.1.3 | Define programme, aims, logistics, schedules etc for Testbed 1. Many sub-tasks. | 13 | Started and meeting regarding event aims and objectives held in September 2018. Testbed 1a completed. Planning document draft 1 ready. Planning team meeting regularly before T-1b in April. | 60 | WP-C2 | UoL
130 | 555 | T-C2.1.1 | Define programme of events in conjunction with partner programmes and organisations. | 6 | Postpone to September 2018. Periodic updates. First programme now finalised with budget and available on Redmine. | 100 | WP-C2 | UoL
131 | 558 | T-C2.2.1 | Washup event Testbed 1. | 24 | Not yet begun. This will be incorporated in the 2nd week of the project meeting. | 0 | WP-C2 | UoL
132 | 504 | T-R3.8.1 | Production of NRT LSTA maps for use in nowcasting. NRT LSTA maps available in data repository. | 14 | Daytime LST anomaly maps are being produced in NRT over a W African domain (20W-20E,0-20N). Average daily LST anomaly maps are automatically uploaded to the SWIFT GWS on JASMIN at /prj/swift/SEVIRI_LST/imgs_dailymean/lst_anom_daymean_$YYYY$MM$DD.png These maps date back to June 2018. From Dec 2018, an E African domain has been added... /prj/swift/SEVIRI_LST/imgs_dailymean/lst_anom_daymean_EAfrica_$YYYY$MM$DD.png | 100 | WP-R3 | CEH
133 | 441 | T-R1.2.3b | Pilotting user interviews and surveys in partner countries and identifying countryfor conducting survey and interview strategy: Phase 1 (Senegal) | 15 | In collaboration with Leeds and ANACIM we have drafted a plan for the workshop that follows the Ghana approach. We are now working on a stakeholder meeting for 13-14 March 2019 that will engage with national users followed by an in depth discussion with technical users. These plans are well developed and we will be followed by a workshop report in April/May 2019. | 30 | WP-R1 | CEH
134 | 543 | T-C1.5.1 | Assign responsibilities for coordination of summer schools and forecaster training events, with associated budgets. | 6 | 2019 Summer School to be held at KNUST. Training for T-1 was held in Togo, Nov 2018. Contribution also made to SWFDP training in Nairobi, Jan 2019. | 100 | WP-C1 | UoL

## users2partners
| id | username | partner
0 | 202 | wsdlhy | CEH
1 | 233 | atgaye | UCAD
2 | 234 | eadefisan | ACMAD
3 | 236 | cbain | UKMO
4 | 237 | mpadi | GMet
5 | 238 | ctaylor | CEH
6 | 239 | dparker | NCAS-AP
7 | 240 | dparker | UoL
8 | 242 | jomotosho | FUTA
9 | 243 | sdanuor | KNUST
10 | 245 | mdiopkane | ANACIM
11 | 246 | zsegele | ICPAC
12 | 247 | tstein | UoR
13 | 248 | lamekudzi | KNUST
14 | 249 | bchanzu | KMD
15 | 229 | earmgr | UoL
16 | 267 | jmutemi | UoN
17 | 268 | ablyth | NCAS-AP
18 | 269 | sjwoolnough | NCAS-C
19 | 270 | wsdlhy | UoR
20 | 271 | wsdlhy | NiMet
21 | 272 | wsdlhy | ACMAD
22 | 273 | wsdlhy | WMO
23 | 274 | wsdlhy | KNUST
24 | 275 | wsdlhy | FUTA
25 | 276 | wsdlhy | GMet
26 | 277 | wsdlhy | UoN
27 | 278 | wsdlhy | NCAS-AP
28 | 279 | wsdlhy | ANACIM
29 | 280 | wsdlhy | ICPAC
30 | 281 | wsdlhy | UoL
31 | 282 | wsdlhy | UCAD
32 | 283 | wsdlhy | KMD
33 | 284 | wsdlhy | NCAS-C
34 | 285 | wsdlhy | UKMO
35 | 286 | eadefisan | UoR
36 | 287 | eadefisan | NiMet
37 | 288 | eadefisan | WMO
38 | 289 | eadefisan | KNUST
39 | 290 | eadefisan | FUTA
40 | 291 | eadefisan | GMet
41 | 292 | eadefisan | UoN
42 | 293 | eadefisan | NCAS-AP
43 | 294 | eadefisan | ANACIM
44 | 295 | eadefisan | ICPAC
45 | 296 | eadefisan | UoL
46 | 297 | eadefisan | UCAD
47 | 298 | eadefisan | KMD
48 | 299 | eadefisan | NCAS-C
49 | 300 | eadefisan | CEH
50 | 301 | eadefisan | UKMO

## users2work_packages
| id | username | work_package
0 | 155 | earmgr | WP-R1
1 | 168 | pantwiagyei | WP-R1
2 | 169 | ataylor | WP-R1
3 | 170 | tstein | WP-R2
4 | 171 | eadefisan | WP-R2
5 | 172 | lamekudzi | WP-R3
6 | 173 | ablyth | WP-R3
7 | 174 | jfletcher | WP-R3
8 | 175 | alahatdiop | WP-R4
9 | 176 | jmarsham | WP-R4
10 | 177 | jmutemi | WP-R5
11 | 178 | jschwendike | WP-R5
12 | 179 | bogwang | WP-R6
13 | 181 | dparker | WP-M1
14 | 182 | dparker | WP-C2
15 | 183 | dparker | WP-C1
16 | 184 | dparker | WP-M2
17 | 185 | cbirch | WP-R7
18 | 186 | sjwoolnough | WP-R6
19 | 188 | wsdlhy | WP-M1
20 | 189 | wsdlhy | WP-R7
21 | 190 | wsdlhy | WP-R5
22 | 191 | wsdlhy | WP-R2
23 | 192 | wsdlhy | WP-R4
24 | 193 | wsdlhy | WP-C1
25 | 194 | wsdlhy | WP-R6
26 | 195 | wsdlhy | WP-C2
27 | 196 | wsdlhy | WP-R3
28 | 197 | wsdlhy | WP-R1
29 | 198 | wsdlhy | WP-M2
30 | 199 | eadefisan | WP-M1
31 | 200 | eadefisan | WP-R7
32 | 201 | eadefisan | WP-R5
33 | 202 | eadefisan | WP-R4
34 | 203 | eadefisan | WP-C1
35 | 204 | eadefisan | WP-R6
36 | 205 | eadefisan | WP-C2
37 | 206 | eadefisan | WP-R3
38 | 207 | eadefisan | WP-R1
39 | 208 | eadefisan | WP-M2

## work_packages
| id | code | name | status | issues | next_deliverable
0 | 45 | WP-R1 | Users and Communication
1 | 46 | WP-R2 | Forecast Evaluation
2 | 47 | WP-R3 | Satellite Remote Sensing
3 | 48 | WP-R4 | Nowcasting
4 | 49 | WP-R5 | Synpotic Methods
5 | 50 | WP-R6 | S2S Forecasting
6 | 52 | WP-C1 | Training
7 | 53 | WP-C2 | Forecast Testbeds
8 | 54 | WP-M1 | Project Management
9 | 55 | WP-M2 | Legacy
10 | 51 | WP-R7 | Convection-Permitting Ensemble Forecasting | One convection-permitting ensemble test case has been completed and evaluated. It is clear that a time-lagged ensemble of deterministic forecasts will provide more spread than full ensemble simulations from a couple of start times. Going forward we will develop a strategy for how to best combine the two. The HyVic research flights over Lake Victoria were successfully completed at the end of January 2019. Some convection-permitting forecasts were run in real-time for this field campaign and testbed1a. These runs successfully forecast dry conditions over the lake and these runs are currently being evaluated against the aircraft observations. We have recently discussed the modelling plan going forward and have agreed to run another set of test ensemble simulations for testbed1b, and then make the final decision about model configuration and ensemble type immediately after that, running the bulk of the past case studies as convection-permitting ensembles between June and December 2019. The main analysis of those runs will be completed in 2020 and 2021. | D-R7.1 has been a little delayed, due to the late start of the WP-R7 PDRA. Beth Woodhams will start in April 2019 and will complete the literature review immediately. | No deliverables are due in the next quarter.