## deliverables
| id | code | work_package | description | month_due | progress | percent | partner
0 | 343 | D-R1.1 | WP-R1 | Report on current state of knowledge regarding user needs for forecasts at different timescales in each sector. | 9 | Submitted on 12th July 2018 | 0 | UoL
1 | 345 | D-R1.3 | WP-R1 | Coproduced forecast communication tools that have been iteratively tested and refined with user groups, and recommendations for good practice. | 41 | Planned completion revised to February 2021 to reflect revised schedule. Elias Nikiaka's contract has been ammended due to his work being part time until August 2018. However he is still scheduled to finish in April 2020 | 0 | UoL
2 | 346 | D-R1.4 | WP-R1 | Joint deliverable with WP-R2: User evaluation of forecast utility developed through direct provider/user interaction and user feedback in 1.2.2a-d, and guide to impact based forecasting | 45 | Not yet begun. | 0 | UoL
3 | 372 | D-R5.6 | WP-R5 | Develop new training material on the realtionship between the synoptic and the meso-scale (e.g. case studies) | 51 | Not yet started. I have, since about May/June 2018, informed that I would not be in a position to carry out this activity due to my other assignments and programmes. | 0 | FUTA
4 | 349 | D-R2.3 | WP-R2 | Reports describing implementation of new metrics for CP ensemble evaluation against satellite data. | 11 | 2% complete. Case studies identified. WP-R7 explained case study design and selection procedure. | 2 | FUTA
5 | 350 | D-R2.4 | WP-R2 | Reports on design and implementation of verification metrics for S2S and probabilistic forecasts and developments to seamless evaluation methodology. | 11 | 5% complete. Case studies identified. | 5 | ICPAC
6 | 351 | D-R2.5 | WP-R2 | Documentation on best practice for forecast evaluation over Africa. | 26 | Not yet begun. | 0 | FUTA
7 | 352 | D-R2.6 | WP-R2 | Training school on best practice for forecast evaluation over Africa. | 38 | Not yet begun. | 0 | UoR
8 | 353 | D-R2.7 | WP-R2 | Baseline evaluation of weather forecast skill and updates as the project evolves, for M&E. | 11 | 2% complete. Met services have provided forecast products that they intend to verify during SWIFT. | 2 | UoR
9 | 354 | D-R2.8 | WP-R2 | Joint deliverable with WP-R2: User evaluation of forecast utility, and guide to impact based forecasting | 45 | Not yet begun. | 0 | UoL
10 | 356 | D-R3.2 | WP-R3 | Report on current status of satellite and radar products used in operational centres and universities. Baseline exercise | 13 | 70% complete middle of Sept 18. A survey is being sent out on 17 August 18 with a due date a week or so later. The report will be written shortly thereafter. It has already been established that none of the African partners are using the EUMETSAT nowcasting system for forecasts. | 70 | UCAD
11 | 358 | D-R3.4 | WP-R3 | Enhanced capacity in African centres for analysing satellite data (all relevant channels) and using satellite products -- as evidenced by good access to products, trained users, training material, use in interpretation of convective rainfall and how best to use in nowcasting. | 47 | Not yet started | 0 | ACMAD
12 | 360 | D-R3.6 | WP-R3 | New well-tested satellite product for improved nowcasting capability | 39 | Not yet started | 0 | UoL
13 | 359 | D-R3.5 | WP-R3 | Phase 1. Case/satistical studies of evolution of storms using satellite products. | 27 | 10% completed. A number of cases have been identified but the ones to be used for this delverable have not been chosen. -JKF\r\n\r\n5% completed. There has been some progress on this deliverable, but good cases still need to be chosen. | 10 | NCAS-AP
14 | 363 | D-R4.1 | WP-R4 | Access to an automated satellite-based storm nowcasting tool/product in SWIFT centres | 51 | NWC SAF working at UoL NCAS with test data\r\nThe SAFNWC is installed in ANACIM but need to be configured | 60 | ANACIM
15 | 367 | D-R5.1 | WP-R5 | Benchmark current operational practice (project document) | 15 | 40% complete - key tasks to achieve this deliverable have been strated | 40 | UoL
16 | 368 | D-R5.2 | WP-R5 | Benchmark current state of knowledge on synoptic systems and HIW over West Africa (project document) | 15 | 30% complete approximately | 30 | NiMet
17 | 369 | D-R5.3 | WP-R5 | Benchmark current state of knowledge on synoptic systems and HIW over East Africa (project document) | 15 | 30% complete approximately | 30 | UoL
18 | 370 | D-R5.4 | WP-R5 | Investigate and evaluate physical processes of synoptic systems in reanalysis | 27 | Not yet started | 0 | UoL
19 | 371 | D-R5.5 | WP-R5 | Evaluate representation of synoptic system in models, i.e. in global and convection-permitting deterministic and ensemble simulations with the MetUM, as well as other operatinally used models such as WRF and COSMO to determine the predictability of deep convection in different synoptic environments in Africa | 51 | Not yet started | 0 | UoL
20 | 373 | D-R6.1 | WP-R6 | Scientific papers on sub-seasonal drivers of variability | 51 | Benchmarking of knowledge of sub-seasonal drivers continues and research has begin on the role of MJO, AEJ and TEJ on W African Monsoon Onset. | 5 | NCAS-C
21 | 362 | D-R3.8 | WP-R3 | Land-surface analysis | 27 | This work (characterising land persistence in response to rain from EO) won't start till April 2020 | 0 | CEH
22 | 355 | D-R3.1 | WP-R3 | Establish a new UK research capability in satellite remote sensing of clouds | 25 | 5 March 2019: still 20% complete as Jennifer is occupied with other deliverables (including for WP C1) and has not had time for the in-depth work required to establish new expertise in satellite remote sensing of clouds. -JKF\r\n\r\n20% complete. The grade 8 position has been filled; Jennifer Fletcher will start in Nov, 2018. The other position will be filled in Jan 2019 and then the networking etc will begin. | 20 | NCAS-AP
23 | 361 | D-R3.7 | WP-R3 | Phase 2. In-depth study of physical processes (dynamics and microphysics) in storms using more advanced satellite data | 48 | 4 March 2019 still not yet started.\r\n\r\nNot yet started | 0 | NCAS-AP
24 | 344 | D-R1.2 | WP-R1 | A report on user perceptions and needs for forecast products for different timescales and sectors in each country. | 27 | Planned completion revised to December 2019 to reflect change in task schedule. | 30 | KNUST
25 | 347 | D-R2.1 | WP-R2 | Reports describing the implementation of eye-witness reports, radar and satellite observations over Africa for verification of severe weather forecasts (both synoptic and NWP). | 26 | 15% complete. Evaluating a case study for Kumasi in June 2018 | 15 | KNUST
26 | 375 | D-R6.3 | WP-R6 | Document(s) on assessment of forecast skill | 51 | Skill assessment is being done for S2S hindcast for 7 models (BoM, CMA, ECMWF, KMA, Meteo France, NCEP, and UK Met Office) over GHA | 20 | ICPAC
27 | 376 | D-R6.4 | WP-R6 | New documented operational products and tools | 51 | Not started | 0 | ACMAD
28 | 378 | D-R6.6 | WP-R6 | Training materials for summer schools | 35 | Preparation fo training materials awaiting decsions on oveally content of summer school | 0 | NCAS-C
29 | 379 | D-R6.7 | WP-R6 | Updated chapter(s) for forecasters handbook | 45 | Not started | 0 | NCAS-C
30 | 380 | D-R6.8 | WP-R6 | S2S forecast testbed | 39 | Planning for the testbed has begun: The format of fortnightly telecons has been agreed. | 0 | ICPAC
31 | 381 | D-R7.1 | WP-R7 | Benchmark current state of knowledge and best practice in convection-permitting ensemble forecasting (project document) | 9 | Delayed due to delay in PDRA recruitment. This task will be assigned to WP-R7 convective ensembles PDRA Beth Woodhams, who starts in April 2019. It will be the first task she performs. New deadline May 2019. | 0 | UoL
32 | 383 | D-R7.3 | WP-R7 | Report on evaluation of ensemble forecast skill and optimal model configuration | 43 | Beth Woodhams will complete this task when she starts in April 2019. Deadline on track. | 0 | UoL
33 | 384 | D-R7.4 | WP-R7 | Report on storm predictability under different synoptic conditions in the context of CP ensemble forecasting | 51 | Will be jointly completed by WP-R5 and R7 PDRAs (Woodhams and Clarke, starting Apr 2019 and Aug 2018 respectively). Deadline on track. | 100 | UoL
34 | 389 | D-C2.3 | WP-C2 | Carry out Testbed 2 (S2S) | 33 | To be conducted after real-time S2S data become available | 0 | ICPAC
35 | 388 | D-C2.2 | WP-C2 | Documentation on Testbed 1 including a paper. | 27 | Planned for April 2019 | 0 | UoL
36 | 391 | D-C2.5 | WP-C2 | Carry out Testbed 3 (nowcasting to synoptic) | 49 | TBD | 0 | UoL
37 | 392 | D-C2.6 | WP-C2 | Documentation on Testbed 3. Papers. | 49 | TBD | 0 | UoL
38 | 393 | D-M1.1 | WP-M1 | Kick-off meeting | 2 | Completed November 2017 | 100 | UoL
39 | 394 | D-M1.2 | WP-M1 | Assurance Documentation | 12 | Completed September 2018 | 100 | NCAS-AP
40 | 395 | D-M1.3 | WP-M1 | Due Diligence | 6 | Ongoing - 80% complete | 0 | NCAS-AP
41 | 396 | D-M1.4 | WP-M1 | Collaboration Agreement | 6 | Completed March 2018 with amendment to insurance request for African partners in August 2018 | 100 | NCAS-AP
42 | 398 | D-M1.6 | WP-M1 | Financial Management Plan | 6 | Completed March 2018 with amendments made September 2018 | 100 | NCAS-AP
43 | 399 | D-M1.7 | WP-M1 | Recruitment | 6 | Completed September 2018 | 100 | UoL
44 | 400 | D-M1.8 | WP-M1 | Budgeting & Finance protocol | 12 | Completed March 2018 with amendments made September 2018 | 100 | NCAS-AP
45 | 402 | D-M1.10 | WP-M1 | Leadership of cross-cutting activities such as fellowships, secondments, summer schools, etc. | 51 | 70% complete - to be finalised September 2018 | 70 | NCAS-AP
46 | 403 | D-M1.11 | WP-M1 | SWIFT 4-Year Plan (calendar of events) | 12 | 70% complete - to be finalised September 2018 | 70 | NCAS-AP
47 | 404 | D-M1.12 | WP-M1 | Scientific reporting | 51 | 70% complete - to be finalised September 2018. First tranche of reporting collected September 2018 | 70 | UoL
48 | 405 | D-M1.13 | WP-M1 | Monitoring indicators (MEL) and MEL protocol | 12 | 70% complete - to be finalised September 2018 | 70 | NCAS-AP
49 | 406 | D-M1.14 | WP-M1 | LogFrame and ToC | 12 | Completed September 2018 | 100 | NCAS-AP
50 | 407 | D-M1.15 | WP-M1 | Communications Strategy | 9 | Completed June 2018 | 100 | NCAS-AP
51 | 408 | D-M1.16 | WP-M1 | Data protocol plan | 12 | In development | 0 | NCAS-AP
52 | 410 | D-M1.18 | WP-M1 | Stage Gate Review | 12 | Completed September 2018 | 100 | NCAS-AP
53 | 411 | D-M1.19 | WP-M1 | Annual reporting to RCUK/GCRF | 18 | Ongoing - first tranche completed September 2018 | 100 | NCAS-AP
54 | 412 | D-M1.20 | WP-M1 | Whole project meeting 2019 | 16 | TBC July 2019 | 0 | NCAS-AP
55 | 413 | D-M1.21 | WP-M1 | Whole project meeting 2020 | 16 | TBC 2020 | 0 | NCAS-AP
56 | 414 | D-M1.22 | WP-M1 | Whole project meeting 2021 | 16 | TBC 2021 | 0 | NCAS-AP
57 | 390 | D-C2.4 | WP-C2 | Documentation on Testbed 2. Papers. | 39 | To be conducted after S2S real time data become available | 0 | ICPAC
58 | 417 | D-M1.25 | WP-M1 | Science Programme Director to travel to African Partner Institutions | 41 | SPD appointed October 2018 | 0 | ACMAD
59 | 386 | D-C1.10 | WP-C1 | Fellowships: advertise, assess and appoint. | 11 | First 3 fellows appointed on schedule. Second round to be advertised (probably need to create a new deadline for this, for the deliverable.\r\nNeed to discuss schedule for next round. | 60 | NCAS-AP
60 | 387 | D-C2.1 | WP-C2 | Carry out Testbed 1 | 21 | Planned for April 2019\r\nTestbed 1a completed successfully. Planning group is active. | 20 | UoL
61 | 401 | D-M1.9 | WP-M1 | Meetings: Exec, Advisory, WPs | 51 | Ongoing throughout the project, but protocol for meetings developed | 80 | NCAS-AP
62 | 397 | D-M1.5 | WP-M1 | Risk Register | 6 | Draft finaliased March 2018, but ongoing throughout the project | 80 | NCAS-AP
63 | 409 | D-M1.17 | WP-M1 | Communications: website, promotional materials, advertising, coordination of articles published, logo, etc. | 12 | Website and logo finalised in April 2018. | 80 | NCAS-AP
64 | 415 | D-M1.23 | WP-M1 | Documentation workshop | 30 | First meeting held in Nairobi, Jan 2019.\r\nSecond meeting to be held in project meeting, Kumasi, 2019. | 50 | NCAS-AP
65 | 377 | D-R6.5 | WP-R6 | Documentation on operational best practice | 51 | Benchmarking survey's of current operational practice analysed and benchmarking report in preparation.\r\nDocuments are gathered on case study and approaches on operational practice. | 20 | ANACIM
66 | 418 | D-M1.26 | WP-M1 | Aligning the WPs (cross-cutting activities) | 14 | SPD appointed October 2018 | 0 | ACMAD
67 | 419 | D-M1.27 | WP-M1 | Development of best practice for university funded GCRF programmes | 14 | 60% complete. Lorraine Youds has written a paper, together with a colleague, on joining-up the project development stage and project initiation stage of programmes and a review of current procedures at the University of UoL to ensure that they are fitfor-purpose for large, international, multi-partner programmes. | 60 | NCAS-AP
68 | 420 | D-M2.1 | WP-M2 | Partnerships: a coordinated set of partnerships which contribute to the SWIFT outcomes. | 14 | Still in development - partnerships have been developed with several global weather programmes and businesses, e.g. BP, HIGHWAY, the YESS network, Rainwatch | 0 | ACMAD
69 | 421 | D-M2.2 | WP-M2 | Documentation of user-needs methodologies. This could be a new Forecasters' Handbook chapter - to be discussed. | 21 | TBD - PSD appointed October 2018 | 0 | ACMAD
70 | 422 | D-M2.3 | WP-M2 | New Handbook chapter on Forecast Evaluation | 39 | TBD - PSD appointed October 2018 | 0 | ACMAD
71 | 423 | D-M2.4 | WP-M2 | Updated Handbook material on Nowcasting for Africa. | 39 | TBD - PSD appointed October 2018 | 0 | ACMAD
72 | 424 | D-M2.5 | WP-M2 | Updated Handbook material on ensemble prediction for Africa. | 39 | TBD - PSD appointed October 2018 | 0 | ACMAD
73 | 425 | D-M2.6 | WP-M2 | Updated Handbook material on S2S forecasting for West Africa. | 39 | TBD - PSD appointed October 2018 | 0 | ACMAD
74 | 426 | D-M2.7 | WP-M2 | Produce a Forecasters' Handbook for East Africa. | 51 | TBD - PSD appointed October 2018 | 0 | ACMAD
75 | 366 | D-R4.4 | WP-R4 | Recommendations on best storm nowcasting practise for the SWIFT region, with appropriate training products and activities | 51 | 15%% survey of existing practices underway, some work started during the Pre test bed 1a | 15 | KMD
76 | 374 | D-R6.2 | WP-R6 | Scientific papers on S2S model evaluation | 51 | 1. Analysis of subseasonal forecast skill for Africa in NCEP, ECWMF and Met Office models is underway, and a paper is in preparation\r\n2. Analysis of forecast skill for Monsoon Onset for CMA, Met Office and ECMWF over Nigeria has been carried out and a paper is in preparation. | 5 | NCAS-C
77 | 348 | D-R2.2 | WP-R2 | Joint deliverable with WP-R4: Reports on nowcasting evaluation against satellite data using new metrics. | 11 | The work has begun already in Ghana where analysis on weather related elements have been investigated and documented through daily and weekly "Chart Discussions" at the GMet Central Analysis and Forecast Office (CAFO). | 60 | GMet
78 | 364 | D-R4.2 | WP-R4 | Documented evaluation of selected automated Nowcasting tool | 51 | GMet in Ghana do not have automated nowcasting tools but the nowcasting is done manually, where models are analysed and synoptic features interpreted to come out with weather forecast. | 60 | GMet
79 | 385 | D-C1.8 | WP-C1 | Summer school 1: many sub-tasks | 10 | Postpone to July 2019 (might have been typo, originally?). Planning will start in earnest in September 2018 at KNUST. We will partner the event with YESS.\r\nPlanning group is active. Advert has now been sent around. | 30 | UoL
80 | 416 | D-M1.24 | WP-M1 | Lead Scientist and Programme Manager travel to partner institutions | 30 | Started November 2018 - ongoing. Doug Parker and Lorriane Youds have visted Dakar, Senegal and Nairobi, Kenya. Visit to Accra and Kumasi, Ghana completed in September 2018.\r\nDue to a reduction in travel commitments, Doug will not go to Nigeria in Spring 2019, but Lorraine plans to go, to coincide with the Users meeting. | 75 | NCAS-AP
81 | 357 | D-R3.3 | WP-R3 | Make satellite products available to African centres | 23 | 5 March 2019: 35% complete: a dish has been installed at Chilbolton and James Groves can access data and run it through the NWCSAF software. No change on the installation/knowledge sharing with African parters -- this will take place during Testbed 1b (April/May 2019) and Summer School (July 2019). This will be very complex given the number of partners who are all at different stages in their current access to the data and software. -JKF\r\n\r\n30% complete approximately. Difificult to determine since the task is so involved. The plan is to get the EUMETSAT products working in UoL on a local compute. Then take disks, or laptops with everything set up and working to the African partners and teach them how to use the products. A satellite dish and decoder will have to be bought by the African parnters for streaming the EUMETSAT data in real time. | 35 | NCAS-AP
82 | 365 | D-R4.3 | WP-R4 | Documented new scientific understanding of: (i) behaviour of convective storms in West and East Africa & dependence on local environment, (ii) the observed relationships between remotely-sensed storm properties and in-situ observations of high-impact weather, with peer-reviewed publications | 51 | 5% Work has not begun in earnest but field work over Lake Victoria is helping to generate hypotheses/research ideas.\r\n\r\n0% - awaiting UoL NCAS PDRA to start \r\n\r\n0% - setting up RDT, getting data, test-beds, summer school have all been priorities | 0 | NCAS-AP
83 | 382 | D-R7.2 | WP-R7 | Creation of a set of CP ensemble forecasts over tropical Africa and prototype post-processed products for research and training. For use by Africa-SWIFT academics and African partners. The forecast data will be available on the Met Office MASS archive for UK academics and will be packaged up appropriately to send to partners as needed. Post-processed products will be provided for the testbeds and other training activities. | 39 | August 2018. 5% complete. At the last WP-R7 meeting the strategy for selecting case study dates was discussed. Partners from across the WPs have suggested interesting case studies. Stu Webster has run one test simulation (as of 17/08/2018). Sam Clarke, who starts 20th Aug. 2018 will analyse that simulation to check everything is working ok, then we will start running further simulations. Deadlines on track.\r\nJan 2019. 35% complete. A convection permitting ensemble was run in real time over Lake Victoria basin during the HyVic pilot flight campaign in January 2019 at 4.4 km and 8.8 km grid length, together with an 8.8 km parametrized convection model. These models were driven by the global N640 18-member ensemble (MOGREPS-G). The same models were also nested inside the \xa0global N1280 deterministic model. All imagery was made available externally on the CEDA website, so that it could be used for \u201cin the field\u201d flight planning. Additionally a 4.4 km Tropical Africa ensemble has now been run for three start times for the first of previously identified case study events \u2013 an event with flooding over Kenya in November 2015. This data is now being analysed by UK universities partners. | 35 | UKMO

## partners
| id | name | country | role
0 | 86 | NCAS-AP | UK | Academic
1 | 87 | NCAS-C | UK | Academic
2 | 88 | UoL | UK | Academic
3 | 89 | UoR | UK | Academic
4 | 90 | CEH | UK | Academic
5 | 91 | UKMO | UK | Operational
6 | 92 | ACMAD | International | Academic
7 | 93 | ICPAC | International | Academic
8 | 94 | ANACIM | Senegal | Operational
9 | 95 | UCAD | Senegal | Academic
10 | 96 | GMet | Ghana | Operational
11 | 97 | KNUST | Ghana | Academic
12 | 98 | NiMet | Nigeria | Operational
13 | 99 | FUTA | Nigeria | Academic
14 | 100 | KMD | Kenya | Operational
15 | 101 | UoN | Kenya | Academic
16 | 102 | WMO | Switzerland | Operational

## tasks
| id | code | description | month_due | progress | percent | work_package | partner
0 | 428 | T-R1.1.1 | Development of reporting template for baselining the current provision of forecasts | 4 | Initial version completed Jan 31st 2018. Ammended and finalised on 9th Feb 2018 (based on Met Office feedback) | 100 | WP-R1 | UoL
1 | 430 | T-R1.1.3a | Completion of 1.1.1 reporting templates for Ghana | 7 | Final version received 13th April 2018 | 0 | WP-R1 | KNUST
2 | 433 | T-R1.1.3d | Completion of 1.1.1 reporting templates for Senegal | 7 | Final version received 27th April 2018\r\nCompleted | 100 | WP-R1 | ANACIM
3 | 432 | T-R1.1.3c | Completion of 1.1.1 reporting templates for Nigeria | 7 | Final version received 5th May 2018 | 0 | WP-R1 | NiMet
4 | 434 | T-R1.1.4 | Draft paper reviewing exisiting literature (peer review and grey literature) on user needs for weather and climate information in West Africa and East Africa | 9 | Draft completed June 2018, final deliverable report submitted on 12 July 2018 | 100 | WP-R1 | UoL
5 | 435 | T-R1.2.1 | Completion of standard protocols for user surveys and interviews | 14 | Delayed due to desire to use outputs of the user-provider workshops in developing protocols. However, due to unavoidable delays holding the workshops, this task will now proceed regardless. New target month is October 2018. Philip Antwi-Agyei to take leadership until ACMAD post appointed. | 0 | WP-R1 | UoL
6 | 440 | T-R1.2.3a | Pilotting user interviews and surveys in partner countries and identifying country strategy for conducting survey and interview strategy: Phase 1 (Ghana) | 15 | Activity initially pushed back until after user workshops. As uncertainty exists over precise workshop timing. New completion date is December 2018. | 0 | WP-R1 | KNUST
7 | 507 | T-R4.1.2 | Documented strategy for access to & development of nowcasting tools | 13 | NWC SAF identifed as akey tool and working at NCAS with test data. Plan to share working version with all SWIFT organisations. Need to document plan.\r\nThe NWC SAF is installed in ANACIM and has to be configured. It is installed in KMD but not working. | 50 | WP-R4 | ANACIM
8 | 442 | T-R1.2.4a | Pilotting user interviews and surveys in partner countries and identifying country strategy for conducting survey and interview: Phase 2 (Kenya) | 17 | Activity initially pushed back until after user workshops. As uncertainty exists over precise workshop timing. New completion date is February 2019. | 0 | WP-R1 | UoN
9 | 443 | T-R1.2.4b | Pilotting user interviews and surveys in partner countries and identifying country strategy for conducting survey and interview: Phase 2 (Nigeria) | 17 | Activity initially pushed back until after user workshops. As uncertainty exists over precise workshop timing. New completion date is February 2019. | 0 | WP-R1 | NiMet
10 | 444 | T-R1.2.5a | Completion of user interviews and surveys: Phase 1 (Ghana) | 19 | Revised to April 2019 following on from changes to pilotting schedule. | 0 | WP-R1 | KNUST
11 | 438 | T-R1.2.2c | ACMAD faciliated workshops bringing together NMS and user representatives in each partner country (Nigeria) | 17 | Everything is set to hold the Users' workshop on 26th and 27th March, 2019 | 20 | WP-R1 | ACMAD
12 | 446 | T-R1.2.6a | Completion of user interviews and surveys interviews: Phase 2 (Kenya) | 22 | Revised to July 2019 following on from changes to pilotting schedule. | 0 | WP-R1 | UoN
13 | 447 | T-R1.2.6b | Completion of user interviews and surveys interviews: Phase 2 (Nigeria) | 22 | Revised to July 2019 following on from changes to pilotting schedule. | 0 | WP-R1 | NiMet
14 | 448 | T-R1.2.7 | Draft paper reporting on the findings of 1.2.5a, 1.2.5b, 1.2.6a and 1.2.6b. | 26 | Revised to Nov 2019 following on from changes to inteview schedule. | 0 | WP-R1 | UoL
15 | 449 | T-R1.3.1 | Table collating evidenced based recommendations for good practice in forecast communication acquired through Tasks 1.1 and 1.2, and through continued review of the peer review and grey literature. | 31 | Revised to correspond with Elias Nkiaka's revised end of contract. | 0 | WP-R1 | UoL
16 | 450 | T-R1.3.2 | Case study examining measureable impact? (e.g. meningitis warnings, fishing fines, crop insurance etc?) | 41 | Revised to Feb 2021 to correspond with other changes in project schedule. Andrea Taylor currently takes responsibility for this. However, as this is further defined "ownership" may change. | 0 | WP-R1 | UoL
17 | 451 | T-R2.1.1 | Archive strategy for radar data | 19 | GMet have provided a report on their radar availability for Accra. The old radar in Senegal is no longer operational. The new radar for the new Dakar airport will be operated by ASECNA.\r\nAccording to T-R3.2.2 (in D-R3.1) there is no working radar in SWIFT centers. One radar installed at Abuja but not yet functional. However the work will be continued for future radar data acquisition | 20 | WP-R2 | ANACIM
18 | 437 | T-R1.2.2b | ACMAD faciliated workshops bringing together NMS and user representatives in each partner country (Kenya) | 14 | It has been proposed that the workshop in Nairobi be delayed until Jan 2019 in order to tie in with testbed planning. | 20 | WP-R1 | ACMAD
19 | 439 | T-R1.2.2d | ACMAD faciliated workshops bringing together NMS and user representatives in each partner country (Senegal) | 17 | Everything is set to hold the Users' workshop on 12th and 13th March, 2019 | 25 | WP-R1 | ACMAD
20 | 498 | T-R3.7.2 | Ghana | 27 | validation of AIRS satellite and NCEP_R2 temperature and RH with DACCIWA and AMMA rediosonde data has been carried out. work done is about 75% complete and manuscript is in preparation | 75 | WP-R3 | KNUST
21 | 429 | T-R1.1.2 | Documentations of governance and institutional arrangements for NMSs | 14 | Work ongoing. Revised planned completion date November 2018 | 0 | WP-R1 | KNUST
22 | 452 | T-R2.1.2 | Identify storm characteristics in dense rain gauge network and satellite data | 20 | 10% complete. Rain gauge data has been gather by Leonard and Jacob at KNUST and by David Koros at KMD. | 10 | WP-R2 | KNUST
23 | 473 | T-R2.7.2 | Document at regular intervals forecast skill and metrics used | 49 | KMD has provided 2018 OND rainfall verification analysis and this is being studied. Waiting for submission by the other three Services. A 4-month frequency is suggested. | 20 | WP-R2 | FUTA
24 | 456 | T-R2.2.1 | N/A (Requires alignment with WP-R4) | 32 | Not yet begun. | 0 | WP-R2 | NiMet
25 | 459 | T-R2.3.3 | Analysis of cases against uniform set of verification metrics | 42 | Not yet begun. | 0 | WP-R2 | ACMAD
26 | 460 | T-R2.4.1 | Select case studies based on S2S archive | 9 | 100% complete. Identified three case studies over East Africa, namely November 2015 and two in MAM 2018. For MAM 2018, most models indicated normal to below normal rainfall, but heavy floods were experienced (above normal). | 100 | WP-R2 | ICPAC
27 | 462 | T-R2.4.3 | Design S2S verification metrics | 31 | Not yet begun. | 0 | WP-R2 | ICPAC
28 | 463 | T-R2.4.4 | Analysis of case studies | 45 | 0% complete. Task commenced Aug-18. | 0 | WP-R2 | ICPAC
29 | 464 | T-R2.5.1 | Document radar use across Africa for verification | 20 | Not yet begun. | 0 | WP-R2 | ANACIM
30 | 472 | T-R2.7.1 | Identify forecasts used for baseline evaluation and relevant metrics and set reporting intervals | 51 | Forecasts used by the Met Services/Agencies have been submitted and collation concluded. Identification forecasts methods used and preparation of baseline information are\r\n on-going | 40 | WP-R2 | FUTA
31 | 457 | T-R2.3.1 | Select case studies suitable for ensembles evaluation (WP-R7) | 33 | Several case studies identified for East and West Africa. Case study design and selection procedure agreed with WP-R7. | 35 | WP-R2 | ACMAD
32 | 468 | T-R2.6.1 | Link up planning with WP-C1 training and test-bed event | 16 | Not yet begun. | 0 | WP-R2 | UoR
33 | 477 | T-R3.2.1 | Report on the current satellite operational products used in African Centres. | 13 | 70% complete by middle of Sept 18. A survey is being sent out on 17 August 18 with a due date a week or so later. The report will be written shortly thereafter. It has already been established that none of the African partners are using the EUMETSAT nowcasting system for forecasts. The report is now completed. | 100 | WP-R3 | ANACIM
34 | 471 | T-R2.6.4 | Online resources post-event | 16 | Not yet begun. | 0 | WP-R2 | UoR
35 | 474 | T-R2.7.3 | Evaluate uptake of verification practices and metrics at operational centers | 48 | Not yet begun. | 0 | WP-R2 | FUTA
36 | 475 | T-R3.1.1 | Hire 2 positions within NCAS. | 16 | 50% complete. The grade 8 position has been filled; Jennifer Fletcher will start in Nov, 2018. NCAS Board has requested that the second position (Grade 6) be filled by an NCAS core person. This will require the person to work at least 50% (for 4 years) on the project, but ideally 100% for 2 years. | 50 | WP-R3 | NCAS-AP
37 | 476 | T-R3.1.2 | Establish current work in field and hold research forum | 26 | Not yet begun. | 0 | WP-R3 | NCAS-AP
38 | 479 | T-R3.3.1 | Sort out how to access and use appropriate EUMETSAT data. | 13 | 40% complete. It\ufffds now possible to access the data (not in real time) . | 40 | WP-R3 | NCAS-AP
39 | 480 | T-R3.3.2 | Determine products and domain required by each centre | 20 | Not yet started | 0 | WP-R3 | NCAS-AP
40 | 481 | T-R3.3.3 | Set up and deliver system with software, satellite data and images, and documentation tailored for individual centre needs | 23 | 5% complete. A start has been made on setting up the system. | 5 | WP-R3 | NCAS-AP
41 | 482 | T-R3.4.1 | Write new training materials (and/or instructions how to use exisiting material) for using satellite products. | 23 | 5% complete. Notes have been made as progress is made. | 5 | WP-R3 | NCAS-AP
42 | 483 | T-R3.4.2 | Produce web pages. | 23 | Not yet started | 0 | WP-R3 | NCAS-AP
43 | 484 | T-R3.4.3 | Train the trainers in using satellite products | 21 | Not yet started | 0 | WP-R3 | NCAS-AP
44 | 485 | T-R3.5.1 | Storms in: Senegal | 27 | Not yet started | 0 | WP-R3 | ANACIM
45 | 486 | T-R3.5.2 | Ghana | 27 | 5% completed. There has been some progress on this deliverable, but good cases still need to be chosen. | 100 | WP-R3 | KNUST
46 | 489 | T-R3.5.5 | Africa? | 27 | Not yet started | 0 | WP-R3 | ACMAD
47 | 490 | T-R3.5.6 | Africa? | 27 | Not yet started | 0 | WP-R3 | NCAS-AP
48 | 492 | T-R3.6.1 | Define the problem to be solved | 20 | Not yet started | 0 | WP-R3 | UoL
49 | 493 | T-R3.6.2 | Design of new product & implementation | 22 | Not yet started | 0 | WP-R3 | UoL
50 | 494 | T-R3.6.3a | Implementation of new product | 26 | Not yet started | 0 | WP-R3 | UoL
51 | 495 | T-R3.6.3b | Test of new product using one or more of case studies in T-R3.5.x. | 32 | Not yet started | 0 | WP-R3 | NCAS-AP
52 | 496 | T-R3.6.4 | Make new product available to African centres. Write documents. Training of key people and set of on-line documents. | 39 | Not yet started | 0 | WP-R3 | ACMAD
53 | 497 | T-R3.7.1 | Storms in: Senegal | 41 | Not yet started | 0 | WP-R3 | UCAD
54 | 454 | T-R2.1.4 | Develop storm statistics tools for use with radar data | 20 | 0% complete. PDRA (Carlo Cafaro) started in January 2019. | 0 | WP-R2 | UoR
55 | 491 | T-R3.5.7 | Evaluate co-variation of observed storm statistics | 15 | 10% complete. PDRA (Peter Hill) has applied offline storm tracking tool on SEVIRI data. | 10 | WP-R3 | UoR
56 | 458 | T-R2.3.2 | Characterise uncertainty in verification statistics | 36 | 0% complete. PDRA (Carlo Cafaro) started in January 2019. | 0 | WP-R2 | UoR
57 | 465 | T-R2.5.2 | Document satellite use for verification | 26 | 0% complete. PDRA (Peter Hill) started in December 2018. Task relies on documenting of forward simulators. | 0 | WP-R2 | UoR
58 | 470 | T-R2.6.3 | Design lesson plan and identify teaching staff | 16 | Not yet begun. NB. Similar task is underway for preparation of Summer School. | 0 | WP-R2 | UoR
59 | 488 | T-R3.5.4 | Kenya | 27 | some case studies have been documented at KMD | 30 | WP-R3 | KMD
60 | 461 | T-R2.4.2 | Land-surface process studies | 12 | This work will not begin until April 2020 | 0 | WP-R2 | CEH
61 | 478 | T-R3.2.2 | Report on current radar facilities and capabilities in African Centres. | 13 | Similar to above, but for radar. \r\nThere is no working radar in SWIFT centres.\r\nThe report is now completed. | 100 | WP-R3 | ANACIM
62 | 500 | T-R3.7.4 | Kenya | 26 | Not yet started | 0 | WP-R3 | UoN
63 | 501 | T-R3.7.5 | Africa? | 48 | Not yet started | 0 | WP-R3 | ACMAD
64 | 502 | T-R3.7.6 | Africa? | 48 | Not yet started | 0 | WP-R3 | NCAS-AP
65 | 508 | T-R4.2.1 | Agreed selection of case-studies (with in-situ data) of high-impact weather affecting African-SWIFT countries for evaluation | 31 | 30%. Some email discussion of some cases, and some investigation of individual cases. UCAD and ANACIM have proposed 4 cases studies of heavy rains that occurred in Senegal from 2012 to 2018. | 20 | WP-R4 | UCAD
66 | 525 | T-R6.5.1 | Benchmark current operational practice | 51 | Survey complete and initial analysis presented to WP telecon. Document prepared and result presented during Skype meeting. | 90 | WP-R6 | ICPAC
67 | 512 | T-R4.3.1 | Archive of satellite data+retrievals & tracked storms available, with remotely sensed properties, & corresponding operational analyses or reanalyses, for target period, for analysis of storm behaviour | 27 | 10% has not been a priority yet, but storm tracking algorithm identified, test satellite data being downloaded | 0 | WP-R4 | NCAS-AP
68 | 509 | T-R4.2.2 | Agreed metrics of user-relevant high-impact weather for nowcasts | 31 | 10% Not advanced since Dakar meeting list | 10 | WP-R4 | UCAD
69 | 510 | T-R4.2.3 | Evaluation of an automated nowcasting tool for the case studies, using remotely sensed & in-situ storm properties | 51 | 5% NWC SAF working with test data at UoL, some case study analysis under way (not with NWC-SAF) | 5 | WP-R4 | UCAD
70 | 511 | T-R4.2.4 | Statistical evaluation of an automated nowcasting tool remotely sensed storm properties, for a selected hindcast period (archiving appropriate data) | 51 | 5% NWC SAF working with test data at UoL | 5 | WP-R4 | UCAD
71 | 514 | T-R4.4.1 | Documented base-line of current status of nowcasting within SWIFT centres | 11 | 70% centres surveyed, not all responses complete | 70 | WP-R4 | KMD
72 | 516 | T-R5.1.2 | Identifying case studies for East and West Africa, which can be used across the whole project | 15 | A questionaire to identify suitable case studies is drafted. | 0 | WP-R5 | UoL
73 | 517 | T-R5.3.1 | Developing objective tracking methods for synoptic scale disturbances in reanalysis and model data | 27 | An objective tracking method has beeen developed and was presented at the last teleconference for WP-R5. | 0 | WP-R5 | ACMAD
74 | 518 | T-R5.3.2 | Providing a data set of objectively identified synoptic systems in reanalysis data | 27 | Work on objectively identyfying HIW weather events is in progress. | 0 | WP-R5 | ACMAD
75 | 499 | T-R3.7.3 | Nigeria | 48 | Not yet started. Accessibility to satellite and radar products is a constraint. | 0 | WP-R3 | FUTA
76 | 520 | T-R5.3.3 | Comparing model performance on selected case studies | 27 | Work is in progress. | 0 | WP-R5 | ACMAD
77 | 521 | T-R5.4.1 | Controls on HIW through physical process studies in models and observations | 51 | Work has now started in all institutions. | 0 | WP-R5 | UCAD
78 | 522 | T-R5.3.4 | Statistical evaluation physical processes of model, analysis and reanalysis data | 51 | The work is in process. | 0 | WP-R5 | UoN
79 | 523 | T-R5.3.5 | Discuss new results on the scale interactions between the meso, synoptic and large-scale over West and East Africa at a meeting and, if possible, update or reformulate existing conceptual models | 51 | We will use the upcoming teleconference to discuss the scietific results from WP-R5. | 0 | WP-R5 | UoN
80 | 524 | T-R5.3.6 | Testing which aspects of existing synoptic models over West Africa are represented in state-of-the-art NWP models at different horizontal resolutions | 51 | Not yet begun. | 0 | WP-R5 | ACMAD
81 | 526 | T-R6.1.1 | Benchmark current state of knowledge | 51 | Initial review of current understanidng underway: | 0 | WP-R6 | UoN
82 | 527 | T-R6.3.1 | Assess forecast skill of operational systems | 51 | Initial analysis of S2S skill underway | 0 | WP-R6 | NiMet
83 | 513 | T-R4.3.2 | Archive of in-situ data of surface weather for statistical evaluation of nowcasts of surface weather, for target hindcast period | 27 | 0% satellite data, test beds, summer school & RDT have been the priorities | 0 | WP-R4 | NCAS-AP
84 | 532 | T-R6.1.3 | Identifying case studies for East and West Africa, which can be used across the whole project (e.g. CP ensembles, devlopment of training materials) | 15 | Contributed to initial case study identification for WP-R7 | 0 | WP-R6 | NiMet
85 | 534 | T-R6.7.1 | Training: Testbeds | 39 | Initial Planning has begun including format and timing of testbed. | 0 | WP-R6 | ICPAC
86 | 505 | T-R3.8.2 | Analysis of persistence of observed land surface variables (LST, LAI) from historical record to inform S2S work. Paper and inclusion in S2S workshop material? | 27 | This work will not begin until April 2020 | 0 | WP-R3 | CEH
87 | 506 | T-R4.1.1 | Documented assessment of nowcasting tools & satellite products available | 13 | 70% complete by middle of Sept 18. A survey is being sent out on 17 August 18 with a due date a week or so later. It has already been established that none of the African partners are using the EUMETSAT nowcasting system for forecasts. | 80 | WP-R4 | ANACIM
88 | 533 | T-R6.1.4 | Analysis of convective permitting ensembles to identify mechanisms of sub-seasonal influence on convective and synoptic scale variability | 51 | Work not started yet | 0 | WP-R6 | NCAS-C
89 | 530 | T-R6.2.2 | Analysis of regime dependent skill of operational forecast systems | 51 | Some work on regime dependent skill for ENSO and MJO has begun\r\n | 2 | WP-R6 | NCAS-C
90 | 528 | T-R6.1.2 | Analysis of observations and reanalysis to identify major drivers of sub-seasonal variability (e.g., MJO, ENSO, QBO, Saharan Heat low, tropical waves, African Monsoon System, land surface)" | 51 | Benchmarking of knowledge of sub-seasonal drivers continues and research has begin on the role of MJO, AEJ and TEJ on W African Monsoon Onset.\r\n | 5 | WP-R6 | NCAS-C
91 | 529 | T-R6.2.1 | Analysis of operational model representation of sub-seasonal drivers of variability | 51 | Weekly forecast of meningitis in the meningitis prone belt of West Africa commenced in Last week of December and it is on-going | 5 | WP-R6 | ACMAD
92 | 515 | T-R5.1.1 | Benchmarking reports on synoptic systems in both observations/reanalysis and models | 15 | The work on the benchmarking reports for East and West Africa is in progress.\r\nThe benchmark report on opretaionnal weather forecasting is almost complete. The other one on synoptic systems and HIW over West Africa is already drafted. | 80 | WP-R5 | ANACIM
93 | 436 | T-R1.2.2a | ACMAD faciliated workshops bringing together NMS and user representatives in each partner country (Ghana) | 14 | Users' Workshop at Ghana was held on 8 - 9th November, 2018. Report already submitted | 100 | WP-R1 | ACMAD
94 | 535 | T-R6.6.2 | Training: Summer Schools | 36 | Not yet started | 0 | WP-R6 | UoN
95 | 536 | T-R7.1.1 | Benchmarking reports on the state-of-the-art in the evaluation and operational use of CP ensembles. | 9 | Delayed due to delay in PDRA recruitment. This task will be assigned to WP-R7 convective ensembles PDRA Beth Woodhams, who starts in April 2019. It will be the first task she performs. New completion date=May 2019. | 0 | WP-R7 | UoL
96 | 537 | T-R7.2.1 | Identifying suitable dates for CP ensemble simulations | 9 | 80% complete. At the last WP-R7 meeting the strategy for selecting case study dates was discussed. Partners from across the WPs have suggested interesting case studies. Stu Webster has run one test simulation (as of 17/08/2018). The rest of this work will be on-going as we analyse incresing numbers of the simulations. | 80 | WP-R7 | UoL
97 | 538 | T-R7.2.2 | Running CP ensemble tests and conducting initial evaluation | 15 | 30% complete. Test simulation now exisits. Sam Clarke, who starts 20th Aug 2018 will analyse the test simulation to check everything is working ok, then we will start running further simulations. | 30 | WP-R7 | UKMO
98 | 539 | T-R7.2.3 | Running the full set of CP ensemble simulations | 39 | 2% complete. One test simulation is complete. Once this is analysed and the case study dates finalised it will be much quicker to run the rest. Deadline on track. | 2 | WP-R7 | UKMO
99 | 540 | T-R7.3.1 | CP ensemble model evaluation vs. global/deterministic forecasts and observations | 39 | Beth Woodhams will perform this task. Deadline on track. | 0 | WP-R7 | UoL
100 | 541 | T-R7.2.4 | Development of prototype forecast products for operational forecastering | 27 | This task will be assigned to WP-R7 convective ensembles PDRA Beth Woodhams. Deadline on track | 0 | WP-R7 | UoL
101 | 542 | T-R7.4.1 | Analysis of storm predictability under different symoptic conditions within an ensemble forecasting framework | 51 | Will be jointly completed by WP-R5 and R7 PDRAs (Woodhams and Clarke, starting Apr 2019 and Aug 2018 respectively). Deadline on track | 100 | WP-R7 | UoL
102 | 544 | T-C1.1.1 | Create skills matrices. | 9 | Not started (ACMAD post not yet filled). | 0 | WP-C1 | ACMAD
103 | 545 | T-C1.1.2 | Collect skills data N times. | 48 | First tranche of African researcher skills data collection completed by August 2018 | 100 | WP-C1 | ACMAD
104 | 546 | T-C1.2.1 | Collect documents describing subject benchmarks for different roles. Identify gaps where benchmarks do not already exist. | 6 | Not started (ACMAD post not yet filled). | 0 | WP-C1 | ACMAD
105 | 548 | T-C1.2.3 | Review priority syllabus development areas. | 24 | Not started (ACMAD post not yet filled). | 0 | WP-C1 | UoL
106 | 550 | T-C1.3.2 | Review outcomes of secondments. | 36 | Secondments not yet started | 0 | WP-C1 | ACMAD
107 | 551 | T-C1.4.1 | Create teaching materials (e.g. powerpoints) from the Forecasters' Handbook chapters. | 12 | Not started (ACMAD post not yet filled). Postpone to December 2018. | 0 | WP-C1 | ACMAD
108 | 552 | T-C1.4.2 | Create teaching materials from new SWIFT research in WP-R1-7. | 48 | Not yet started | 0 | WP-C1 | ACMAD
109 | 553 | T-C1.4.3 | Collaborate with Met Office to enhance International Meteorologist training | 36 | Not yet started | 0 | WP-C1 | UoL
110 | 554 | T-C1.8.1 | Review outcomes of fellowships. | 36 | Not yet started | 0 | WP-C1 | ACMAD
111 | 556 | T-C2.1.2 | Baseline assessment of forecaster-researcher links in relation to Africa. | 15 | Not yet started | 0 | WP-C2 | ACMAD
112 | 559 | T-C2.3.1 | Define programme, aims, logistics, schedules etc for Testbed 2. Many sub-tasks. | 13 | Started and meeting regarding event aims and objectives held in September 2018 | 0 | WP-C2 | ICPAC
113 | 560 | T-C2.4.1 | Washup event Testbed 2. | 33 | Not yet begun. | 0 | WP-C2 | ICPAC
114 | 561 | T-C2.5.1 | Define programme, aims, logistics, schedules etc for Testbed 3. Many sub-tasks. | 37 | Started and meeting regarding event aims and objectives held in September 2018 | 0 | WP-C2 | UoL
115 | 562 | T-C2.6.1 | Washup event Testbed 3. | 45 | Not yet begun. | 0 | WP-C2 | UoL
116 | 453 | T-R2.1.3 | Review of microwave forward simulators | 20 | 20% complete. PDRA (Peter Hill) has done a preliminary review of the literature as well as a review of simulators used in the Met Office model. A deadline for a draft report has been set for April 2019, prior to Testbed 1b. | 20 | WP-R2 | UoR
117 | 455 | T-R2.1.5 | Develop storm statistics tools for use with satellite data | 20 | 10% complete. PDRA (Peter Hill) has applied offline storm tracking tool on SEVIRI data. | 10 | WP-R2 | UoR
118 | 469 | T-R2.6.2 | Prepare lecture and exercise materials (Python scripts, sample data) | 16 | Not yet begun. NB. Similar task is underway for preparation of Summer School. | 0 | WP-R2 | UoR
119 | 503 | T-R3.7.7 | Evaluate co-variation of observed storm statistics | 27 | Not yet begun. | 0 | WP-R3 | UoR
120 | 431 | T-R1.1.3b | Completion of 1.1.1 reporting templates for Kenya | 7 | completed | 100 | WP-R1 | KMD
121 | 466 | T-R2.5.3 | Document other verification practice (rain gauges, damage reports, AWS) | 44 | Verification data,verification results and exchange of best verification practices through test bed 1a on 24th to 29th Jan 2019 are ready. | 35 | WP-R2 | KMD
122 | 519 | T-R5.1.3 | Identifying the key synoptic features over East Africa | 15 | First draft of the benchmarking report for East Aftica "Synoptic Systems and High Impact Weather over Eastern Africa" by Jemimah Gacheru is finished.First draft of the paper sent to the WP lead in August 2018 . | 40 | WP-R5 | KMD
123 | 547 | T-C1.2.2 | Agree and document priority syllabus development areas, to include "hard" and "soft" skills. | 12 | Not started (ACMAD post not yet filled). Responsibility to pass to ACMAD or ANO once ACMAD post is filled.\r\nNeed to postpone due date to month 18. | 0 | WP-C1 | UoL
124 | 549 | T-C1.3.1 | Create secondment call, including criteria, process, assessment committee. | 12 | Postpone to December 2018\r\nPostpone to June 2019. | 0 | WP-C1 | NCAS-AP
125 | 557 | T-C2.1.3 | Define programme, aims, logistics, schedules etc for Testbed 1. Many sub-tasks. | 13 | Started and meeting regarding event aims and objectives held in September 2018.\r\nTestbed 1a completed. Planning document draft 1 ready. Planning team meeting regularly before T-1b in April. | 60 | WP-C2 | UoL
126 | 555 | T-C2.1.1 | Define programme of events in conjunction with partner programmes and organisations. | 6 | Postpone to September 2018. Periodic updates.\r\nFirst programme now finalised with budget and available on Redmine. | 100 | WP-C2 | UoL
127 | 558 | T-C2.2.1 | Washup event Testbed 1. | 24 | Not yet begun.\r\nThis will be incorporated in the 2nd week of the project meeting. | 0 | WP-C2 | UoL
128 | 504 | T-R3.8.1 | Production of NRT LSTA maps for use in nowcasting. NRT LSTA maps available in data repository. | 14 | Daytime LST anomaly maps are being produced in NRT over a W African domain (20W-20E,0-20N). \r\nAverage daily LST anomaly maps are automatically uploaded to the SWIFT GWS on JASMIN at\r\n/prj/swift/SEVIRI_LST/imgs_dailymean/lst_anom_daymean_$YYYY$MM$DD.png\r\nThese maps date back to June 2018. From Dec 2018, an E African domain has been added...\r\n/prj/swift/SEVIRI_LST/imgs_dailymean/lst_anom_daymean_EAfrica_$YYYY$MM$DD.png | 100 | WP-R3 | CEH
129 | 441 | T-R1.2.3b | Pilotting user interviews and surveys in partner countries and identifying countryfor conducting survey and interview strategy: Phase 1 (Senegal) | 15 | In collaboration with Leeds and ANACIM we have drafted a plan for the workshop that follows the Ghana approach. We are now working on a stakeholder meeting for 13-14 March 2019 that will engage with national users followed by an in depth discussion with technical users. These plans are well developed and we will be followed by a workshop report in April/May 2019. | 30 | WP-R1 | CEH
130 | 543 | T-C1.5.1 | Assign responsibilities for coordination of summer schools and forecaster training events, with associated budgets. | 6 | 2019 Summer School to be held at KNUST.\r\n Training for T-1 was held in Togo, Nov 2018. Contribution also made to SWFDP training in Nairobi, Jan 2019.\r\n | 100 | WP-C1 | UoL
131 | 531 | T-R6.2.3 | Developing methods to identify tropical waves in real-time forecasts and reanalysis data | 27 | Preliminary work on identification of tropical waves in observations and forecasts underway. Some metrics has been developed to track AEW over West Africa based on their 700 hPa relative vorticity from 2000 to 2015. Now we are trying to investigate the physical properties of such waves and their link with extremes rains events | 15 | WP-R6 | UCAD
132 | 467 | T-R2.5.4 | Document S2S verification practice | 48 | A survey has been conducted in Regional Climate Centers (ICPAC/ACMAD) and NHMSs in east and West Africa. A report prepared. Further clarification needed on "Month Due" to give the appropriate percentage | 90 | WP-R2 | ICPAC
133 | 487 | T-R3.5.3 | Nigeria | 17 | Work has started on various case studies of high impact and/or widespread storms. A particular high impact event which occurred between 23rd - 28th May 2018 and affected both Nigeria and Ghana, is being focused for detailed analysis. Data for these are already being downloaded for the critical analysis. Hoever, accessibility to satellite and radr products has and is a constraint. | 10 | WP-R3 | FUTA
134 | 445 | T-R1.2.5b | Completion of user interviews and surveys: Phase 1 (Senegal) | 19 | Revised to April 2019 following on from changes to pilotting schedule.\r\nIt's about doing user surveys. The report will be available after the user workshop scheduled for March 13th and 14th, 2019 in Senegal.\r\nThe dates of the workshop are set as well as the place, the number of participants and the targets. The budget is also developed as well as the terms of reference of the workshop. The invitation letters will be sent soon. | 10 | WP-R1 | ANACIM

## users2partners
| id | username | partner
0 | 302 | jfletcher | NCAS-AP
1 | 303 | ahartley | UKMO
2 | 202 | wsdlhy | CEH
3 | 233 | atgaye | UCAD
4 | 234 | eadefisan | ACMAD
5 | 236 | cbain | UKMO
6 | 237 | mpadi | GMet
7 | 238 | ctaylor | CEH
8 | 239 | dparker | NCAS-AP
9 | 240 | dparker | UoL
10 | 242 | jomotosho | FUTA
11 | 243 | sdanuor | KNUST
12 | 245 | mdiopkane | ANACIM
13 | 246 | zsegele | ICPAC
14 | 247 | tstein | UoR
15 | 248 | lamekudzi | KNUST
16 | 249 | bchanzu | KMD
17 | 229 | earmgr | UoL
18 | 267 | jmutemi | UoN
19 | 268 | ablyth | NCAS-AP
20 | 269 | sjwoolnough | NCAS-C
21 | 270 | wsdlhy | UoR
22 | 271 | wsdlhy | NiMet
23 | 272 | wsdlhy | ACMAD
24 | 273 | wsdlhy | WMO
25 | 274 | wsdlhy | KNUST
26 | 275 | wsdlhy | FUTA
27 | 276 | wsdlhy | GMet
28 | 277 | wsdlhy | UoN
29 | 278 | wsdlhy | NCAS-AP
30 | 279 | wsdlhy | ANACIM
31 | 280 | wsdlhy | ICPAC
32 | 281 | wsdlhy | UoL
33 | 282 | wsdlhy | UCAD
34 | 283 | wsdlhy | KMD
35 | 284 | wsdlhy | NCAS-C
36 | 285 | wsdlhy | UKMO
37 | 286 | eadefisan | UoR
38 | 287 | eadefisan | NiMet
39 | 288 | eadefisan | WMO
40 | 289 | eadefisan | KNUST
41 | 290 | eadefisan | FUTA
42 | 291 | eadefisan | GMet
43 | 292 | eadefisan | UoN
44 | 293 | eadefisan | NCAS-AP
45 | 294 | eadefisan | ANACIM
46 | 295 | eadefisan | ICPAC
47 | 296 | eadefisan | UoL
48 | 297 | eadefisan | UCAD
49 | 298 | eadefisan | KMD
50 | 299 | eadefisan | NCAS-C
51 | 300 | eadefisan | CEH
52 | 301 | eadefisan | UKMO

## users2work_packages
| id | username | work_package
0 | 155 | earmgr | WP-R1
1 | 168 | pantwiagyei | WP-R1
2 | 169 | ataylor | WP-R1
3 | 170 | tstein | WP-R2
4 | 171 | eadefisan | WP-R2
5 | 172 | lamekudzi | WP-R3
6 | 173 | ablyth | WP-R3
7 | 174 | jfletcher | WP-R3
8 | 175 | alahatdiop | WP-R4
9 | 176 | jmarsham | WP-R4
10 | 177 | jmutemi | WP-R5
11 | 178 | jschwendike | WP-R5
12 | 179 | bogwang | WP-R6
13 | 181 | dparker | WP-M1
14 | 182 | dparker | WP-C2
15 | 183 | dparker | WP-C1
16 | 184 | dparker | WP-M2
17 | 185 | cbirch | WP-R7
18 | 186 | sjwoolnough | WP-R6
19 | 188 | wsdlhy | WP-M1
20 | 189 | wsdlhy | WP-R7
21 | 190 | wsdlhy | WP-R5
22 | 191 | wsdlhy | WP-R2
23 | 192 | wsdlhy | WP-R4
24 | 193 | wsdlhy | WP-C1
25 | 194 | wsdlhy | WP-R6
26 | 195 | wsdlhy | WP-C2
27 | 196 | wsdlhy | WP-R3
28 | 197 | wsdlhy | WP-R1
29 | 198 | wsdlhy | WP-M2
30 | 199 | eadefisan | WP-M1
31 | 200 | eadefisan | WP-R7
32 | 201 | eadefisan | WP-R5
33 | 202 | eadefisan | WP-R4
34 | 203 | eadefisan | WP-C1
35 | 204 | eadefisan | WP-R6
36 | 205 | eadefisan | WP-C2
37 | 206 | eadefisan | WP-R3
38 | 207 | eadefisan | WP-R1
39 | 208 | eadefisan | WP-M2

## work_packages
| id | code | name | status | issues | next_deliverable
0 | 54 | WP-M1 | Project Management
1 | 51 | WP-R7 | Convection-Permitting Ensemble Forecasting | One convection-permitting ensemble test case has been completed and evaluated. It is clear that a time-lagged ensemble of deterministic forecasts will provide more spread than full ensemble simulations from a couple of start times. Going forward we will develop a strategy for how to best combine the two. The HyVic research flights over Lake Victoria were successfully completed at the end of January 2019. Some convection-permitting forecasts were run in real-time for this field campaign and testbed1a. These runs successfully forecast dry conditions over the lake and these runs are currently being evaluated against the aircraft observations. We have recently discussed the modelling plan going forward and have agreed to run another set of test ensemble simulations for testbed1b, and then make the final decision about model configuration and ensemble type immediately after that, running the bulk of the past case studies as convection-permitting ensembles between June and December 2019. The main analysis of those runs will be completed in 2020 and 2021. | D-R7.1 has been a little delayed, due to the late start of the WP-R7 PDRA. Beth Woodhams will start in April 2019 and will complete the literature review immediately. | No deliverables are due in the next quarter.
2 | 45 | WP-R1 | Users and Communication | Work continues to progress on WP-R1. We have completed work on our first project deliverable (Report on current state of knowledge regarding user needs for forecasts at different timescales in each sector). A paper based on this review has been submitted to Environmental Research Letters. Currently, we are in the process of running user-provider workshops in each partner country. These have been delayed from the previous schedule in order to ensure budget transfer, person availability and that workshops don\u2019t clash with national election periods. However, the workshop in Ghana has been completed (8-9th Nov 2018) and a policy brief prepared to share with the wider SWIFT community and a general audience. Following on from the Accra workshop KNUST and GMet plan to run a similar event with users based in the north of Ghana (June 2019). Workshops in Senegal (March 13th-14th 2019) and Nigeria (March 26th-27th 2019) are now scheduled with preparations ongoing. The workshop in Kenya is being planned to coincide with Testbed 1b (April/May 2019). Data gathered in these workshops will be combined with data from the reporting templates completed with each NMS, surveys conducted in each country in producing our second project deliverable (Rport on user perceptions and needs for forecast products for different timescales and sectors in each country). | Tasks R1.1.2 (Documentations of governance and institutional arrangements for NMSs), has been merged with the provider-user workshops. It was originally envisaged that this task could be accomplished using material gathered through NMS reporting templates (Task 1.1.3a-d) and interviews conducted at the SWIFT kick-off meetings, however it has become clear that more data is needed to do this. Rather than pursue this as a standalone activity, institutional arrangements will be explored through the provider user workshops, with user perceptions of these additionally being assessed through subsequent user surveys. Tasks R1.2.1 (Completion of standard protocols for user surveys and interviews) and subsequent piloting have been delayed. However, a survey with farmers and fishermen in Northern Ghana has been piloted by KNUST, and we are using this as a basis for developing a survey protocol that can be applied across context, with some country-specific and sector-specific modifications made | We have no deliverables scheduled for completion during the next quarter. However, we will complete Task R1.2.2a-d (Workshops bringing together NMS and user representatives in each partner country).
3 | 48 | WP-R4 | Nowcasting | Good progress with developing a plan to give access to RDT products: RDT working in Leeds, being setup to work with a big dish for African data, plan to handover to African centres in 2019 summer school. Base-lining complete, with no centres actively using automated nowcasting. Some case studies in African centres. | Development of metrics delayed - will revisit at next WP3/Wp4 telecon | none
4 | 49 | WP-R5 | Synpotic Methods | (Juliane & Joseph \u2013Updated by Joseph 22FEB2019) Actual science work started during 2018 with tasks T5.1, T5.2, T5.5, and T5.8. Task 5.1 has contributed to two deliverables D5.1 and D5.2 due during reporting period 1. D5.1 has been compiled to more than 50%. It requires few inputs from GMet and ANACIM to become 100%. Its current form is good of comments. Task 5.1 is also contributed to D5.2. D5.2 is a more comprehensive project document and is has been well coordinated and written under leadership of NiMet. Task 5.2 on identification of case studies for use in both East and West Africa was completed. These cases identified as implied in the issues of advancing the science of operational weather forecasting in Africa building up on the baselines contained in D5.1 and D5.2. Tasks 5.4, 5.5 and 5.8 are the content of current science work in both East and West Africa and will proceed to the end of SWIFT. Some of the weather data sets, tools and models being used in the research include operational reanalysis (mainly ERAI & NCAR-NCEP), models and weather data post-processing capabilities and forecast models in the \u201cSYNERGY\u201d tool. Following task 5.4, D.3 will be completed during the reporting period 4. | To ensure D5.1 has valid facts from the SWIFT Africa National Meteorological Services (NMSs), Gmet and ANACIM have been requested to provide few statements on human resources and simple map to show the country network of meteorological stations as basis upon which SWIFT will be starting from when addressing operational and research weather data in East and West Africa. | D5.3 during reporting period 4 (i.e. month 24)
5 | 46 | WP-R2 | Forecast Evaluation | The WP overall is on track. The data gathering exercises of D2.1, including understanding which data are available and suitable for forecast verification, are making good progress. All other deliverables depend on these tasks in D2.1 to be near completion before these can get fully underway, including the documentation. Apart from access to observations, the WP tasks also rely on forecast product availability for evaluation and therefore efficient communication with other WPs. Most tasks have persons associated with other WPs and the adoption of "Slack" is helping efficient communication. | The monitoring and evaluation tasks associated with deliverable D2.7 need to be put into place now for this to work well across the SWIFT timeline. The reporting strategy for these tasks will be confirmed at the next telecon (14 March). Several tasks and deliverables have inappropriate "planned completion" dates. These are currently being reviewed on Slack. | No deliverables are due until November 2019 (D-R2.1)
6 | 53 | WP-C2 | Forecast Testbeds | Testbed 1a successfully completed and some important lessons learned, operationally and scientifically. Plans are in good shape for 1b and 2. | No obvious concerns. | Testbed 1b.
7 | 55 | WP-M2 | Legacy | A list of high impact weather (HIW) case studies of weather systems on national and bub-regional scales have been compiled and hosted on the wiki page of the Project. | No problems is envisaged for now | This list of case studies will be investigated across WPs for cross-work packages and holistic approach for the investigation will commence.
8 | 47 | WP-R3 | Satellite Remote Sensing | Case studies of evolution of storms using satellite products, Inter-Comparison of AIRS and NCEP R2 Temperature and Relative Humidity Pro\x0cles with AMMA and DACCIWA Radiosonde Observations over West Africa has been caried out. In addition, TRMM thunderstorm and lightning data has been downloaded and this data analysis is about 40% complete | Manuscript from the temperature and humidity will be soon be submitted | Upcoming deliverable is about 70% complete for KNUST
9 | 50 | WP-R6 | S2S Forecasting | This work package can broadly be divided into three categories: (i) improving our understanding of the drivers of sub-seasonal variability over Africa; (ii) Evaluation (including skill) of sub-seasonal prediction systems; (iii) S2S Forecast testbed and work is progressing in each of these. Much of this work is being developed within analysis of case studies which can cut across the WP. i)\tDrivers of sub-seasonal variability Work has begun on analysing the role of the MJO on rainfall over West Africa and in particular its relationship to Monsoon Onset. Based on AEW tracking developed in WP5 we will also explore the sub-seasonal drivers of AEW variability. Work has begun more generally on Monsoon Onset in West African Partners. A more broad review of existing knowledge of sub-seasonal drivers is underway. ii)\tSub-seasonal forecast skill The S2S database has been used to assess forecast skill for weekly rainfall over the whole of Africa, including some preliminary assessment of skill conditioned on MJO phase; Monthly Rainfall over East Africa, including model biases; and Monsoon Onset for Nigeria, including assessment of the representation of the TEJ and AEJ. Papers are in preparation on each of these analysis. iii)\tS2S Testbed: The testbed is planned to begin late in 2019 with the timing dependent on the access to realtime data, an application to S2S for realtime access to the archive has been made. The S2S project hopes to make realtime access available for 2 years in which case we will extend the testbed for a second year compared to the intial 1 year plan. Some work has begun on developing scripts to allow routine preparation of forecast products from the database. A key aspect of the testbed will be interaction with forecast users (a requirement for realtime access to the S2S database), and it is important that we start to develop these interactions well before we have realtime access to the archive. We have performed a benchmarking survey of current operational practice and a document based on the analysis is in preparation. | We are still waiting to hear whether we will be granted realtime access to the S2S database. At the minimum we will have access to the NCEP data (publicly available) and we could extend to include SubX models. We are also having preliminary discussions with the Met Office about access to their data. | None due, although we expect to submit a number of papers contributing to D-R6.1 and D-R6.2 (and will form the basis on a benchmarking of forecast skill for D-R6.3) during the coming months as well as benchmarking for current operational practice for D-R6.5
10 | 52 | WP-C1 | Training | Some successful activities have been achieved, including computational training in June 2018 (Ghana, with DARA), and joint training with SWFDP (Togo, Nov 18 and Nairobi, Jan 19). However, the strategic aspects of this WP are overdue and need attention. | Communications in this WP have not been very effective. The meetings involve a large number of people, but the engagement can be quite passive, and we have not made progress on some important aims. In particular, we need to move quickly on the baseline activities in regard to skills, existing training, and gaps in provision: all these are overdue. We have some great opportunities to influence the training centres, which need to be taken. Note that there is an international initiative to develop integrated training for the BIP-M: we need the African SWIFT members to engage with this. | We need to defer the due dates for several tasks, but make sure they are done soon. This probably means sharing responsibilities more widely.